## OCR Content
OCR CONVERTED: MPR August 2025-1.pdf
Converted using Optical Character Recognition
OFFICE OF THE EXECUTIVE ENGINEER PWD_ELECT DN UDAIPUR
PHYSICAL AND FINANCIAL PROGRESS OF BUILDING WORKS
Month August 2025
Provision for Expenditure
St. Date of
No Name of Name of Work we = vest Likely Expected ¦ Present physical progress & remarks if,
. Building a aaa men completion date ¦ Till last Month ¦ in next 3
months
W.O.
Amount
Compe
10 12
SaeTRIC a SiON
4059-80-051-03-06-16-P-V
AMC Work of APFC Panel Installed at ¦ 05/2024-25 5
2024 .
1 0.09 ¦ Rs.057) C% — ¦py Court Campus Udaipur 547-549 0.49 ¦ 31.08.2024 wc 0.25 ang ¦ WE SEB tobe prepared atsubidivision
0.66 Campus 30.08.2025 level
22.08.2024
AMC of fire Fighting Detection System] 1 /9924-25
2024 Court —_¦at DJ Court Campus Udai ; 31.08.2024
- Rs. 15.48 pus /Calpur 562-564 os wc 7.83 WC & FB to be paid
15.48 , Pal
Campus 22.08.2024 30.05.2025
' AMC Work of Window and Split AC's 14/2024-25 ;
2024 Court : 08.09.2024
0.17 ¦ Rs 1.17 at DJ Court Campus Udaipur 605 -607 07.09.2025 0.50
1.34 Campus 30.08.2024 07.09.2025
4 Bas Court AMC Work of APFC Panel Installed at ¦ 12/2025-26 o1.08:209
) : 09.2025
- Rs. 0.64 DJ Court Campus, Udaipur (FY 2025- 480-482 ; 30.06.2026 Wr
0.64 ¦ Campus [76 ) 0eeOs 30.06.2026
5 AMC Work of Window and Split AC 13/2025-26
2025 Court 08.09.2025
/ Rs. 1.29 at DJ Court Campus ,Udaipur (FY 483-485 07.09.2026 work to be started
1.29 Campus 3925.26) 738 3005 07.09.2026
6 i. AMC of 3 nos Passenger Elevator 14/2025-26
2025 Court Make (Thyssen Krupp) at Court ; 14.08.2025
7.77 ° Retell Campus ¦Complex at DJ Court ‘36; Sos 3.51 13.06.2026 13.06.2026 0.00 0.00
Campus, Udaipur(FY 2025-26
7 \ AMC of Fire Fighting & Detection 15/2025-26
2025 ’ Court System at DJ Court Campus, Udaipur Gur 22.08.2025
- Rs. 16.25 490-492 13.96
16.25 sue ¦ Campus ¦(FY 2025-26) 90402 5108 2026 ¦ 21-08-2026 0.00 0.00
4059-80-051-03-03-17- (40% Plan+60%CSS)
Court Dismantling reinstallation and 2 Floor 11/2025-26 14 = .
¦) mel? 289.08 ¦ Rs. 90.81¦ Complex {Extension of ¦ nos Elevators in Court 365 8.48 ripe 2025 23.07.2026 0.00 0.00 _ [Existing machine room to be dismantled by
379.89 Udaipur _¦Complex Building Udaipur 14.07.2025 072026 civil wing
4059-80-796-05-00-17-(SF 40% and CF 60%)
1 Electrical Fitting Work in POCSO 09/2025-26
2023 ¦ 3045 ¦Rs 62.50] POCS° {Court in New Court Complex Udaipur 316 10.07.2025 ¦ 99 19.2026 Roof conduit laid
L. 367.00 Court 01.07.2025 09.10 2026
4059-80-05 1-03-06
2025
1.60 - Rs. 1.60
4210-03-105-03-90-17-P
2012 Rs A
ie 943.39 219.52 Medical
ADJ Court
Repairing of Faulty Electric Panel
Installed at ADJ Court Kherwada,
District- Udaipur
20/2025-26
517-519
13.08.2025
1.38
22.08.2025
21.10.2025
21.10.2025
0.00
Fire Protection and Fire Alarm system
work for Auditorium RNT Medical
College Udaipur Job 357/4210
106/2016-17
2237-2239
13.02.2017
13.49
SITC of Sound and Light work in New
122/2017-18
20.02.2017
19.02.2019
31.03.2018
30.09.2018
P¦ 88, ¦ 22 fag Medical ¦Auditorium at RNT Medical College 1880-1882 25.81
Udaipur Job 357/4210 21.03.2018
4210-03-796-01-02-17-V-P
SITC of 15 Passenger Cum Strecher in
MBGH Porch at RNT Medical College 49/2024-25
2024 R 7 Udaipur and 10 Passenger in
- s. 60.00] Medical 1199-1201
60.00 Administrative Building at RNT 13.01.2025
Medical College Udaipur :
4210-03-789-01-02-17-P-V
Fire Fighting and Fire Detection
2023 ; System Work in Shri Sunder Singh 09/2024-25
33.50 10.76 ¦Rs.22.74¦ Medical ¦Bhandari Hospital Ambamata Udaipur 559-561
. 22.08.2024
8443 Dep I
T ]E/F Work in 5 No Class Room Girls 60/2022-23
196.75 ¦ Rs23.25¦ Deposit ¦College Kherwara Udaipur 1622 8.00
16.01.2023
AMC of Fire Fighting system in SSB at ¦ 08/2024-25
Rs. 14.11 Deposit ¦MBGH Udaipur 556-558 11.88
22.08.2024
AMC of Fire Fighting System in 15/2024-25
0.55 ¦Rs. 14.47) Deposit ¦MBGH, Campus Udaipur 716 12.81
26.09.2024
Supply of Electricians for general ¦
Maintenance in Main Building MBGH 60/2024-25
. 15.51 Deposit _¦Hospital Udaipur (Fy 2025-26) 1288 4.91
28.01.2025
Supply of Electricians for general 61/2024-25
15.51 Deposit Maintenance in RNT Medical College 1289 492
Udaipur (Fy 2025-26) 28.01.2025
Supply of Electricians for general
Maintenance in Trauma Block & near 62/2024-25
Rs. 15.51) Deposit — ¦py building, Udaipur (Fy 2025-26) 1290 3.29
28.01.2025
24.01.2025
23.07.2025
20.06.2021
28.03.2022
23.09.2025
3.94
4.05
Maintenance work in progress
FB (3.22) Time Ext. case in Progress
Currently at Division office for some
objection removal
WC and HO
WC & Final Bill (19.82)to be
paid.EOTcase approved by CE office
MBGH lift istallation completed and
Admin block lift installtion in progress
31.08.2024
30.01.2025
30.01.2025
11.21
6.50
WC & FB pending due to LOC HO due
26.01.2023
25.07.2023
31.08.2024
30.08.2025
05.10.2024
04.10.2025
01.02.2025
31.01.2026
01.02.2025
31.01.2026
25.07.2023
0.00
7.00
0.00
W.C,& HO Final bill pending due to
LOC.
WC & FB to be prepared at sub division
04.10.2025
31.01.2026
31.01.2026
2.20
2.46
01.02.2025
31.01.2026
31.01.2026
1.64
Deposit
13.33
1371.5
2023
2375.00 2077.50 ¦Rs. 297.50
Medical
653.14 ¦ Rs. 95.90
511.12 ¦ Rs. 65.52
409.09 ¦ Rs. 46.92
Electricfication Work at Exhibition
Hall for Organization centre of study of
Value District Udaipur
Dismentalling of Old Ac,s in New OPD
at MBGH Campus, Udaipur
76/2024-25
1420
17.02.2025
77/2024-25
1417
17.02.2025
18.02.2025
17.06.2025
18.02.2025
17.05.2025
¦
WC & HO FB to be paid after reciving
deposit from civil division
WC & HO due FB to be prepared at sub
division level
Electrification Work of Critical Care
unit at RNT Medical College Udaipur
Electrification work of repair and
Modernization of Existing EMRS at
Rishabhdeo Distt, Udaipur.
91/2024-25
1592
20.03.2025
04/2025-26
179-181
19.05.2025
29.03.2025
28.06.2026
28.05.2026
27.05.2026
28.06.2026
27.05.2026
Electrification work for Repair and
Modernization of in EMRS Kotra,
Residential Quarters type-II (G+1)-11,
type-II(G+2)-3 and Repair and
Maintenance of School and Hostel
Kotra, Udaipur.
Electrification work for Repair and
Modernization of existing EMRS at
Dadiya, Gogunda Distt. Udaipur
06/2025-26
185-187
19.05.2025
08/2025-26
260-262
17-06-2025
aa ¦
51.12
28.05.2025
27.05.2026
26.06.2025
25.09.2026
27.05.2026
25.09.2026
2nd floor roof casted partially
School and Hostel Maintenance work
started, wiring work is in progress
Wiring work in progress at Hostel block
Layout given to contractor work started
5 ¦ Rs. 97.00
1045.50 ¦ 748 s
Electric Cabling and Maintenance
Work in Sahelion ki Bari, Udaipur
16/2025-26
497-499
13.08.2025
22.08.2025
21.09.2025
21.09.2025
Hire Charges of Temporary lighting
Work for VVIP Visit in City area
Udaipur
89/2023-24
1256
08.02.2024
17.02.2024
16.02.2025
30.09.2025
E/F Work of I.T.I College Building at
kanore Distt Udaipur
Electrification of ACJM Residence
. . Il at Vallabha nagar
tial Quarters Type
Rs. 7.50 ¦ Residential Distt Udaipur
84/2023-24
1072
08.12.2023
06/2024-25
550-552
22.08.2024
17.12.2023
16.06.2025
30.09.2025
31.08.2024
30.08.2025
Wiring work completed and Accessories
work in progress Electric connection
demand paid
WC & Electrical Connection due, demand
note paid
———
ee
4216-01-700-03-!
90-17
Sai Electrification of Residential Quarter 05/2025-26
1 35.39 ¦ Rs. 3.72 ¦ Residential ¦for SDO at Gogunda, Udaipur 182-184 28.05.2025
39.11 19.05.2025 3.08 27.05.2026 27.05.2026 0.00 1.00 Down boxes work completed
5054-CRIF
Line Shifting Work Gogunda Tula
2024 Machind Bada Bhanuja Gaon Jhalon ki 63/2024-25 08.02.2025
2921.51 2868.85 ¦ Rs. 52.66 ¦ CRIF Road ¦Madar Sayon ka Kheda Sangath 1299 35.80 07.02.2026 30.12.2025 0.00 10.00 Pole shifting work in progress
Rajsamand Road 0/0 to 14/500 30.01.2025 i.
Udaipur
ELECTRIC SUB DIVISION-II
2059-80-053-01-(01)-21-P
2024 Providing of Labour for day to day 17/2024-25 25.10.2024
4.00 2.07 Rs. 1.93 Electric Maintenance Work in Govt. 796 4 10.2025 24.10.2025 1.49 0.00 WIP
. Non Residential Building Udaipur 16.10.2024 i
2024 Electric Repair & Maintenance Work 22/2024-25 2024
300 ¦ 143. ¦ Rs.0.57 of Non Residential Govt. Building at 899-900 0.57 ore ; 0.00 0.00 WC & FB to be paid
: Udaipur 08.11.2024 ¦ “
Electric Repair and Maintenance Work ¦ 39/2924-25 F ae
3 oa 3.93 Rs. 2.07 NRB of Non Residential Govt. Building 983 epee 0.53 0.00 WGeakB a be — unis division
. Udaipur 22.11.2024 —
Electric Repair and Maintenance Work 84/2024-25
4¦ 2024 . Rs. 2.00 NRB___¦of Non Residential Govt. Building at 1493 01.03.2025 0.00 0.00 WC & FB to be paid
2.00 Udaipur (2024-25 Qtr.-3) 28.02.2025 30.05.2025
4202-01-796-05-01-17-P
> ° 2 1
1 E/F in Maharana Acharya Sanskrit 12/2022-23 4
2021 Rs 64.06 : . 18.07.2022 Work Completed HO due
498.82 434.76 Lacs Education ¦College at Udaipur 614-616 36.09 17.07.2023 25.04.2024 13.21 15.00 (Budget Allotment is pending )
07.07.2022
4202-01-203-01-90-17-P
1 Electric Repair and cai of 69/2024-25 ‘seems: Wiring and fixture work completed
2024 ¦ 77.20 ¦Rs.21.80¦ Education ¦itls Hostel Meera Girls College 1389 16.97 ¦ vr oe one ¦ 15.09.2025 Electrical panel work completed and
99.00 ; Udaipur 14.02.2025 14.08.202 ‘ finishing work in progress ,
4225-04-800-01-01-17-P
Electric Work in 100 baded Girls 04/2023-24
enor inori i ~ Wiring & Fixture work completed
2017 Minority ¦Hostel of Minority Deptt Udaipur 387-389 64.32 05.08.2023 30.09.2025 10.92 30.00 ng & ¦ ‘
519.37 437.47 ¦ Rs.81.90 Department os 0704 04.08.2024 Finishing work in progress
2216-05-053-01-08-21-P
Electric Repair Work in Govt. 32/2024-25 22.11.2024 ;
ha - ¦ Rs. 1.50 ¦ Residential ¦Residential Ist & IInd Building Udaipur 982 148 ¦ 31089008 wc 0.00 1.00 WC & FB to be paid
1.50 0S.
¦ 22.11.2024
2216-05-053-01-07-21-P
Electric Repair Work in Govt.
Residential Vth Building Udaipur
(2024-25 Qtr -2)
Residential
Residential
Providing of Electrician for Govt
Residential Vth Building, Udaipur
(2024-25 Qtr.-3)
Electrification in Extension work of
Vigyan Chetna Samiti Building,
Udaipur
Repairing of HT & LT Cables at
Rajsathan Sahitya Academy Hiran
Magri Sec-4 Udaipur
Shifting of Electric LT Panel and Other
2025 ; Electric repair work at Rajasthan
7 0.63 Ran05 Deposit Sahitya Academy Hiran Magari Sec.-4
Udaipur
4059-80-051-01-01-17-P
1 023 E/F Work in Sub Tehsil Building at
144.65 ¦Rs. 15.61] Revenue ¦Diwer Distt. Rajsamand
160.26
2 2023 SITC of ACs in Sub Tehsil Building at
160.26 144.65 ¦ Rs. 15.61} Revenue ¦Diwer Dist. Rajsamand
2-01-203-01-90-17-P
E/f in Govt College Building
Kumbhalgarh Rajsmand Job No
00/4202
2018
‘e19
600.00 Rs 61.95
538.05 College Edu
4202-03-102-01-00-17
E/F Work in High Level Sports
2023 RS Facilities and wrestling Academy and 10/2025-26
2600 ¦ 2446-96 ¦ 153 94 Stadium —_ Stadium in Sardarpura Nathdwara Distt 345
, Rajsamand. 08.07.2025
Laboratory room at first floor Aryabhatt
34/2024-25
980
22.11.2024
22.11.2024
21.05.2025
WC & FB to be prepared at sub division
21.05.2025 level
85/2024-25
1498
28.02.2025
53/2024-25
1245-1246
20.01.2025
18/2025-26
503-505
13.08.2025
19/2025-26
506-508
13.08.2025
39/2024-25
1095
17.12.2024
17/2025-26
500-502
13.08.2025
14/2019-20
385-387
05.08.2019
01.03.2025
28.02.2026 2b MaB026
21.01.2025
20.07.2025
WC & pending due to deposit not received
22.04.2025 from civil division
0.00 1.88
22.08 2025
21.10.2025 21.10.2025
21.10.2025
30.07.2025
21.10.2025
23.02.2023
16.10.2026
Maintenance work in progress
22.08.2025
21.10.2025
Maintenance work in progress
26.12.2024
25.12.2025
Work completed and HO EB sent to
treasury for payment
22.08.2025
21.10.2025
Work completed and HO due
Work Completed and Handed over. EOT
approved from ACE office FB sent to
treasury for payment.
15.08.2019
14.11.2020 30.43
5.65
17.07.2025
Roof casted in admin block and ground
16.10.2026
floor in indoor stadium
0.00
8443 Dep-lll
2023 SITC of Sound system, stage draprey &¦ 66/2023-24 18 10.2023
1 970.81 ¦ Rs. 52.47) DMFT — ¦Stage Lighting System in Auditorium at¦ 880-882 41.37 09.12.2024 4.52 35.00 WC and HO FB pending due to LOC
1023.28 ; 17.10.2024
Khamnore Distt Rajsamand 09.10.2023
92.57 ¦ Rs. 7.43 School ¦ E/F Work in Classroom at Namana 7102334 18.10.2023 we 5.50 WC and HO FB sent to treasury for
Education ¦School (Nathdwara) Distt Rajsamand 17 10.2024 payment
School —_¦E/F Work in Govt School Ssi2023-28 17.12 2023 Half portion roof casted, Down conduiting,
3 319.03 ¦ Rs. 30.97 ori Sovt schaolat 1073 30.10.2025 soo ¦" i casted.
Education ¦Gavguda(Nathdawara) Distt Rajsamand 08.12.2023 16 03.2025 in progress, Civil work progress ts slow
30 06.2024
29.12.2025
— ¦
Beis F 01/2024-25
5864.00 ¦Rs. 866.00 Dmet | ¦EF Workin District Hospital Building 265 15.12.2025
at Nathdwara Distt. Rajsamand
4 21.06.2024
: E/F Work in Classroom at Govt. Senior ¦ 41/2024-25
2023 92.70 ¦ Rs.73
100.00 - 7.30
63.37 ¦ Rs. 4.76
School
Education
17 01.2025
16.11.2025
Secondary School Railmagra Distt. 1172
Rajsamand 09.01.2025
E/F Work in 4 Nos. Classroom at Govt. ¦ 74/2024-25
Sr. Sec. School at Kanadev ka Guda 1404
Distt. Rajsamand 14.02.2025
30.10.2025
School
Education
15.02.2025
14.11.2025
30.10.2025
Roof casting in progress at various levels
0.00 jon FF,SF and down conduit and boxes work
in progress
0.00 Roof casted and down conduiting work in
, progress
0.00 Roof casted and down conduiting work in
4 progress
aed rr, 75/2024-25
Schoo! E/F Work in Library Building at 1407 15.02.2025 30.09.2025 Civil work stopped roof to be casted
Education ¦Balkrishna School Rajsamand 14.07.2025 :
14.02.2025
Fire Fighting Work in District Hospital 78/2024-25 02 Layout given to Cont, tobe
Building at Nathdwara Distt 1435 slog aose ¦ 31.05.2026 0.00 a her iaiiiaie
Rajsamand 19 02.2025 —
90/2024-25 Ground Floor & first floor roof Casting in
E/F work in 59 beded MCH building at 19.03.2025 Progress, down conduit, DB and boxes
rat : 1530 30.07.2026 ,
Bhim Dist. Rajsamand 18.09.2026 work in progress at ground floor and First
10.03.2025 floor
E/F Work in Classroom at Govt. School¦ 02/2025-26 -
ooo ¦ 9478 ¦ Rs.5.22 Cane Kunthwa (Nathdwara) Distt. 26 eines 11.01.2026 0.00 ¦ Wiring work completed and fixture work in
: Rajsamand 03.04.2025 wre eee
E/F Work in Classroom at Takadiyon 03/2025-26 Pe
ae 92.60 ¦ Rs. 7.40 ne ka Gudha (Mandiyana) School Distt. 27 hotness 11.01.2026 Roof casted and dawn conduiting work in
Rajsamand 03.04.2025 siamese progress
P
E/F Work in New Govt. LT.I Building
at Bhim Distt Rajsamand Wiring Work, accessories work completd
37/2023-24 in admin block. Wiring work and cabling
ae 24.09.20 i
Building 627 73.03 os 15.10.2025 work completed in work shop block ground
12.09.2023 —
floor, at Ist floor wiring work in progress,
Electrical connection demand note paid
5038 E/F Work in Hall Room in District 01/2025-26
21.81 ¦ Rs.2.72 ¦ Building ¦Statistics Office Rajsamand. 25 12.04.2025 ¦ 44 19.2095 Roof to be casted
24.53 pio anes 11.10 2025 0.
~U
Divisidgal/ Accountant
. Executive Engineer
PWD Elect. Dn Udaipur PWD Elect Dn Udaipur
Last Month
August (in Nos)
OFFICE OF THE EXECUTIVE ENGINEER PWD ELECT. DN. UDAIPUR
Last to last Month
oti
=
¦ 5 fro of Security Deposit to be Refunded
of ah Tein bagmce
Divisidnal Accountant Executive Engineer
PWD Elect. Dn Udaipur PWD Elect. Dn. Udaipur