## OCR Content
OCR CONVERTED: New Doc 10-30-2025 13.39.pdf
Converted using Optical Character Recognition
178824
Governmont Of Rajasthan
WAM Innerlouter shoot
Month/Year :
Jul/2025
Department Name : Public Works Department
VD DIV BENESHWAR DHAM (DUNGARPUR)(42908)
Dataied Wam bill of: XEN PV
BaFor Works Payment : WAM Payment
OfficelO
Reference No : 4383690 Wam Reference No ; #2/3 of 1287343
: 42908
osion Name : XEN PWD DIVISION BENESHWARDHAM HQ Division Code: 104 Bill No : 65178824
ASPUR ¦
nes + 44007/2025 DemandNo :; 30 DDOCoda : 42908
As : JDHO02952F ObjectHead : 74 Budget Head : 5054-04-796-07-00/SF/V
r : 616616,00 NonPlan : 0,00 NA > 0.00 ContigencyHead :
TO. ye Treasury/Sub Treasury OfficerASPUR
Please Order to pay % 400677 as per the claim contained in this bill
Sign of Clerk Sign of DA Sign of Divisional Officer
{certified that ¦ have personally examined and satisfied myself about the guinness of claim that the claimed bill is strictly in accordance with rules and that th
said partiesifirm details mentioned in wam bills are correct and said parties/firm are entitled for such payment and this drawal is within the limites of online allotted
budget’LC. .
9 ¦ certified that the compliance of directions/instructions of PWF & AR has been ensured for this bill.
Sign (With Seal)/e-Sign/Digital ESign of DDO
9414724969
Bank Name Invoice No. _-Gross Amt WAMID Budget Head
Address Account No. Invoice Date(In _..» ¢. Nel Amt Deduction Amt
Mobile IFSC Code CaseOf — | ¢ & Par
Branch Name Supplier)’
1 MS Shree Bajrang BANK OF BARODA 20 4 YO 616616.00 4383690 0230-00-800-06-00
Construction 15860200000022,, ’ 4900-01-01 400677.00 4624.00
Village Padli Gujreshwar Post BARBOGENJIX os . & we” 0853-00-102-01-01
Sansarpur Distt. Dungarpur Pin GENJI, DIST. DUNGARPUR; 13873.00
Code 314404 RAJASTHAN > 2059-80-001-04-01
9414724969 a 43654.00
2059-80-052-04-01
10914.00
3054-03-337-01-03
16370.00
8443-00-106-00-00
1387.00
8443-00-108-00-00
111244.0C
8658-00-1 12-00-00
4624.00
8658-00-139-00-00
9249.00
Gress Amount Rs. 6166 16.00 B.T.Amount: Rs. 215939.00 Net Amount:Rs. 400677.00
sunt In Words : FOUR LAKH AND THOUSAND SIX HUNDRED SEVENTY SEVEN Only
Sign Of DDO with Seal/e-Sign/Digital ESign of DDO
Treasury Voucher
No: Date :
Pay & ! | 616616.00
SIX LAKH SIXTEEN THOUSAND SIX HUNDRED SIXTEEN ONLY
(In Words)
B.T. Heads : 215939.00
Osan
SW rat Contents relat : :
i edt Sf sible for It. Forward Time:1 1/07/2025 08:24 PM
Y National i to this bill are provided by Head of Office/DDO and he she Is solely respo Peck nese auce 42 Fal
‘Ormatics centre, Rajasthan State Unit (http:/paymanager.ra}.nic.in) Group Nama:5054 SC Missing Link BA UCRV
°
G Scanned with OKEN Scanner
prance No :55178827
Govornment Of Rajasthan
WAM Innerfouter sheet
nent Code : 65 Department Name : Public Works Department
failed Wam bill of : XEN PWD DIV BENESHWAR DHAM (DUNGARPUR)(42908)
For Works Payment : WAM Payment Reference No
+ 4383691
jision Name =: XEN PWD DIVISION BENESHWARDHAM HQ Division Coda: 104
PUR
ie 1907/2025 DemandNo ; 54
x : JDHO02952F ObjectHead ; 74
: 806344.00 NonPlan + 0.00
NA ; 0.00
, The Treasury/Sub Treasury OfficerASPUR
Please Order to pay ¥ 523959 as per the claim contained in this bill
Sign of Clerk
d satisfied myself about the gu
aid parties/firm details mentioned in wam bills are Correct and said parties/fir
judgeV/LC.
Name Bank Name Invoice No.
Address Account No. Invoice Date(In
Mobile IFSC Code CaseOf
Branch Name Supplier):
4 MS Shree Bajrang BANK OF BARODA
} Construction 15860200000022
\ Village Padli Gujreshwar Post BARBOGENJIX 8 2
Sansarpur Distt. Dungarpur Pin GENJI, DIST. DUNGARPUR:
Code 314404 JRAJASTHAN be
9414724969 “ %
Gross Amount Rs, 806344.00
B.T.Amount: Rs. 282385.00
Osa
SNy Mer» Alco,
Coursey Naor elated to this
tre, Rajasthan State Unit (http://paymanager.raj.nic.in)
inness of claim that the claimed billis s
™ are entitled for such payment and thi
\ certified that the compliance of directions/instructions of PWF & AR has been ensured for this bill.
Pount In Words : FIVE LAKH TWENTY THREE THOUSAND NINE HUNDRED FIFTY NINE Only
onsible for it.
matin bill are provided by Head of Office/DDO and hel she Is up Name'5054 ST Missing Link BA UCRV
cen
ry. Ne \S7 562%)
23)7 ¦20S
Month/Year: Jul/2025
OfficelD : 42908
Wam Reference No : #3/3 of 1287343
Bill No > 65178827
DDOCode + 42908
Budget Head : §054-04-789-05-00/SFIV
ContigencyHead :
Sign of DA
Sign of Divisional Officer
trictly in accordance with rules and that the
S drawal is within the limites of online allotted
Sign (With Seal)/e-Sign/Digital ESign of DDO
9414724969
y'Gross Amt WAMID
Budget Head
rae Net Amt Deduction Amt
* 806344.00
4383691
523959.00
0230-00-800-06-00
6048.00
0853-00-102-01-01
18142.00
2059-80-001-04-01
57086.00
2059-80-052-04-01
14272.00
3054-03-337-01-03
21407.00
8443-00-106-00-00
1815.00
8443-00-108-00-00
145473.00
8658-00-112-00-00
6048.00
8658-00-139-00-00
12094.00
Net Amount:Rs. 523959.00
Sign Of DDO with Seal/e-Sign/Digital ESign of DDO
Date:
806344.00
EIGHT LAKH AND SIX THOUSAND THREE HUNDRED FOURTY
282385.00
Forward Time:11/07/2025 08:24 PM
Print Date & Time:25/07/2025 12:42 PM
CE Scanned with OKEN Scanner
282385.000nly
523959,00
(In Words) : FIVE LAKH TWENTY THREE THOUSAND NINE HUNDRED FIFTY
NINE ONLY
AAO-IAl Treasury/Sub Treasury Officer ESign
Forward Time:11/07/2025 08:24 PM
25/07/2025 12:42 PM
d hel she is solely rasponsibla for ink BAUCRV Print Date & Time
ated to this bill are provided by Head of Office/DDO an Group Nama:S054
\ Courts Ml conten
It
sey National ine
.raj.nic.in)
Mmatics centre, Rajasthan State Unit (http://paymanager. raj
G Scanned with OKEN Scanner
—
3. 7B Ato. £342—
14.
Ic
_ wewen ween ¦S 2016 ¦ \S 7s
oarert aren Fra — Sey Oy SRR bm
que AG .. Sih, semauavpnestessterttin
ord A Stak wal, 4 OZ. Kah hex lace, pai Rhaget.
ard ater em Is2d3 7 Rela 0520. coattet | a.LIGLBL EA»
aahrat earafa Wea
Veen eneneeeeceeeneaeesesoeneenenne
Veevevereverernereusevsonecersenscesseccecnseoe
Stee eee ne ener eeeenneen son senecncoons.
aaah ven ae Se
¦ vier ve olelaz twa a babi beane
ara ph at A Rie LZ P
wen AMIE. FA TH BA A UNS. a mace
Tennessee, _ SAREBTR sea
45. Ma WR YG IT GH. ccsnees a
os eveeveversevseseenees
DATA Banner ssemrnnnnene ata aftrertt —
Beene ceeencanecerecessensseneceuseraesereceeaeeaseneenereLaseunseeuaseSeSEEOSGs esses neesssbesioedsiearer sense
8443-00-108-00-00 eee,
(2) | fedifsie v
8443-00-108-00-00 S00000-=mp tor LIb
8658-00-112-00-00
, sownanti1oVi0 Re Rs. ZALY bec 0
(6) aR Gemma 0230-00-800-06-00 Rs. Ly
6) -Arghit Vac 0853-00-102-01-01
@) | Sxared. 8443-00-106-00-00 1b
(8) fafeer Ray (Taree) 0059-80-800-02-00 Rs.
(6) - wera eae 0030-02-103-01-00 Rs ——
(10) @at APT aaeit , Rs
(1) Brees ant Ya PITA Rs
(12) pet fret at UR Rs
(43) Shreadt at UAT (48 wierd) Rs
3SS79>ED
seen ¦¦ Is Yoo
G Scanned with OKEN Scanner
\ gptf URI © A168 19 104. ST Sat
sees sd TT pel Sar Bry, Ode B
CRO avi tre ~~
id Way ¦
(yoni tC lefloe ae! mA Worle Sfudedl ¦
on gor) iA bys
t op trher ao a
Yee
re 19/3/25.
' Sam a a ,
lsh aed. Lin of ia
G Scanned with OKEN Scanner
GOVE Form RPWA 26
RNMENT oF RAJASTHAN
Date:
No& P ,
d on Nae: EN PWD DIV BENESHWAR Djiay ayManager Rof. Ids): 4383689, 4383690, 4383691
WNGARPUR) Division Code: 42908
] ‘ ail Ref No: 129, Dated: 11/07/2025
A
al payments must invariably be made On forms printed on yellow
aper whi j ‘
nye Payments) Pap ich should not be used for intermediate
has been Payment and (2) Payments for measured work. The form of
Printed separately, should be attached, where necessary]
fot Contractors — This form provides for
( Account Secured advances, which
yok Order Name: Strengthning and Widening of BT Road from Punjpur to Kanthdi Khermal road Km.0/00 to 12/00
jendor Name: MS Shree Bajrang Construction
Budget Head: (shown in ‘Debit head / Payment from' table)
No./ Sanction No.: 1528
Nork Order Agreement Reference Number: 109/2023-24
ub Bill No.: 5 Running
bank IFSC Code: BARBOGENJIX
Bank AccountNo.: 15860200000022
Commencement Date: 27/08/2023 Stipulated Completion Date:
I i ;
27/05/2024 Actual Completion Date:
MB Date (Last): 29/06/2025 MB No: 1942 MB Page(s): 34-42
MB Done By: Vijay Pal Katara jen MB Chked By: Mahesh Ahari Aen Inspecting Authority: Shilpa Patidar
Aspur Xen
Photo uploaded (with date): Yes, 21/06/2025 Physical Progress completion stage: 34 %
Unit ¦ Rate ¦ Quantity executed as per ¦ Payment on the basis of ¦ Remarks _
¦ Measurement Book actual measurements
¦
¦ ¦ Uptodate ¦ Since ¦ Uptodate ¦ Since
¦ previous bill ___ ¦ Previous bill
ee ee ee HH § ¦ 7 [8
tho (As per enclosed bill (Physical) No. & Date, Amount as per pass order of the bill)
Total Van ono ec ee
oe of work done to date (A): 2,50,25,259
allel value of
work shown on previous bill: 20827734
~— Stal a ¦
Prysee Current bill (1-2=3) (F):4197525 - 4 I
. “Vn words) Rupees Forty One Lakh Ninety Se
A ere net
n Thousand Five ¦
usand Five Hundreds Twenty Five Only — :
Courtesy: https://wam.rajasthan.gov.in (Printed on 7/11/2025 2:01:17 PM)
CE Scanned with OKEN Scanner
tified that
aaation 1 and quite from the quantities Of Work actua
In done in connection w; , lly executed, as shown in column 4 of A
yally been with severa i own in column 4 of Account, some work
\s at nate amount of secured advances, if litems and the value of such work (after deduction there from the
aries he co
rope ments, which will be made as soon as posse in anticipation of and subject to the result of detailed
1e28"' ork has been done as per Specification
; , S, ' .
i phe is outstanding against Contractor regarding te areement * Drawings found satisfactory.
iN ools & Plants has rites henviae to the Contractor ‘
Merial has been used by Contractor as per Specify at
1 Nal ment of lade is not drawn previously ations.
7 ils of the Contractor/Supplier h
Y gank Detal ‘ Pplier has been checked 8 veri
¦ al formalities & Steen regarding necessary entries are reno examined
“quality Control Certificate (if required) is attached, ¥ examined.
1 Time Extension Sanction (if required) is attached.
: performance guarantee/BG etc (if any) is under Currency period.
pebit head / Payment from: a
waiteNoce.. He sda.
H 04. 20-04. & it pe
ROSES 20-01TaVP ¦ 2938268¦ Workld: 214297
2 ¦ §054-04-796-07-00-74.V.P om
_ 545678) Workld: 214297
713579 ¦ Workld: 214297
1 ¦ 8443-00-106-00-00
“2 ¦ 8443-00-108-00-00 590000) Deposit-Vih (MD5) (6443)
3 ¦ 0853-00-102-01-01 ¦ 106717¦ Mines & Minerals / Royalty
4 ¦ 0230-00-800-06-00 35572) Labour Welfare
5 ¦ 8443-00-108-00-00 _ 355723) Deposit-ll (SD2) (8443)
6 ¦ 8658-00-112-00-00 35572¦ Income Tax
T ¦ 658-00-190-00-00 nla Deduction
This Bill will break in following part(s) for PayManager (Fisrt column will be RefNo to pull it on PayManager)
rie
4383689
5054-04-337-20-01-74-V-P
8658-00-139-00-00
8443-00-108-00-00
8658-00-112-00-00.
0230-00-800-06-00
0853-00-102-01-01
8443-00-106-00-00
8443-00-108-00-00
arcana tnt at mc ne rt
¦ 2059-80-001-04-01-98-V-P
Prorata
Prorata
3054-03-337-01-03-98-V-P oe Provata___ __—
5054.04, FORT 0TAAP ¦ 545678) Workld: 214297
Courtesy: https://wam.rajasthan.gov.in (Printed on 7/11/2025 2:01:17 PM)
G Scanned with OKEN Scanner
4393690 “¦ 9658-00-112-00-09
pone
8443- 00-10 106- 00-( 5-00-00
*0280-00-600-06.99 ~~} r
¦ 0853-00-102-01-01. > —
‘Payment ‘Through Treasury a an
2059-80- -001-04-01-98-V-P 7
~ 70938) Prorata Workld:
214297 ¦
/2068- 80-052-04- -01-98-V-P_ +— il ee Pr orata _
toa 01-03-08. B aN [P Told
oe ‘5054-04-789-05-00-74-V-P : oN im 214297
8658-00-139-00-00 — —
8443-00-108-00-00 —*/¦ Ss yoga t
8658-00-112-00-00 ¦ we =
0230-00-800- 06- 00
¦ 0853-00 -00-102-01-01 ¦ ™N al — —
as -00-106-00-00 i mas {—_——_———
8443-00-108-00-00
[ Payment Through Treasury
¦ 5054-04-789- 06.0074 92765
2059-80-001-04-01-98-V-P ¦ 57086
Prorata Workld:
214297
Prorata
Se a
2059-80-052-04-01-98-V-P ¦ 14272 Prorata
3054-03-337- 01- 03- 98-V-P_ ¦ Prorata
Net Amount Payable In Figures: 3082125
(InWords): Rupees Thirty Lakh Eighty Two Thousand One Hundreds Twenty Five Only
Dated:
For u isierral Office
(fire orétrer)
b Sisnature of SrRAPR AD Ramis aay a arfipentifye Rap seal
lamar aro, 5 eT OTA a —T. ; ~ tina rs Parte; ——)
oo Save
Courtesy: https://wam.rajasthan.gov.in (Printed on 7/11/2025 2:01:17 PM)
G Scanned with OKEN Scanner
icnwar pham Vr. No. — Date Bill Submitted By the Contractor
es RPWA From No. 26 & 27B
Referred to PWE & A Rules 418, 421, 506 & 507
ment must invariably be made on form printed on yellow P.
aper Which should not be used for Intermediate payment
ontractor & .
(for c & suppliers only for payments for work or supplies actually measured)
¦ Vth Running ACCOUNT BILL
¦
final Pay’
vouser NO Dated sseneneavnns
tot or supplier Bajrang Construction “
ifcol
yor’ Strengthing and Widening of B
¦ g of BT Road from Punjpur Kanthadi Khermal Km 0/0 to 12/0.
tts pill: Vth Running Bill and date of the previous bill for this work - IIrd Running Bill
Ne.
ors ordet | Aggreement No. 1528/17-08-2023 Ag, No. 109/2023-24
ence
f raven order to commence work : 27-08-2023 Stipudate date of completion :- 27-05-2024
' ‘on of work: WIP a i :
att completion © Date of Mesurment: 14.06.2025, 15,06.2025, 17.06.2025, 19.06.2025 &
29.06.2025
& “Sub-works” of estimate)
¦ - ACCOUNT OF WORK OR EXECUTED OR SUPPLIES
Item of work supplies mee ¦e Since Provisional bill (Total 4
Up-to-date for each sub head) E
a :
(grouped under "Sub-heads"
executed (or
Supplied) since!
last certificate
B Clearing and grubbing road land including
uprooting rank vegetation, grass, brush, shrubs,
saphirigs and trees of girth upto 300mm,
removal of stumps, disposal of unserviceable
aterial and stacking of serviceable Material
upto 1000m from road boundary. (MoRTH
Specification : Clause 201).BY
MECHANICAL MEANSIn area of Light
Jungle:
sAhwork in excavation for roadway in soil,
ncluding stacking / disposal of surplus
Material exclusive of compensation of earth.
(MoRTH specification : clause 301 to 305).By
Hydraulic Excavator CK-90 of 0.9 cum bucket
capacity and tipper with disposal upto 1000
mtrs.
ape ork in excavation in ordinary rock,
nCluding stacking / disposal of surplus
Material exclusive of compensation of earth.
(MoRTH specification : clause 301 to 305).By
Hydraulic Excavator CK-90 of 0.9 cum bucket
capacity and tipper with disposal upto 1000
Earthwork in excavation for roadway in hard
éck, including stacking / disposal of surplus
Material exclusive of compensation of earth.
(MoRTH specification : clause 301 to
305).Blasting prohibited.By Mechanical
fion of embankment with approved
efial obtained from borrow-pits with all
grading to requi
vibratory roller 8-10 tonne to m
of Table 300-2 including cost o
for earth taken from private land with lead upto
1 km as per MoRTH Specification : Clause No.
305.
f compensation
CE Scanned with OKEN Scanner
Construction of embankment with ap proved
Materials deposited at site from mi
cutting and excavation from drain and ”
foundation of other structures graded and
compacted by vibratory roller 8-10 tonne to
meet requirement of Tale 300-2 as per MoRTH
specification : Clause No. 305
Used for filling from cutting qty,
No.(i), (ii) & (iii)
Construction of sub-grade and earthen
shoulders with approved Material obtained
from borrow-pits with all lifts and leads,
transporting to site, spreading, grading to
require slope and compacted by vibratory roller
8-10 tonne to meet requirement of Table 300-2
as per MoRTH specification : Clause No. 305,
as per Item
am
Providing, laying and spreading of granular sub
base by providing close graded Material,
mixing in a mechanical mix plant at OMC
carriage of mixed Material to work site,
spreading in uniform layers with motor grader
on prepared surface and compacting with
vibratory power roller to achieve the desired
density, complete as per clause 401. By Mix in
Place Method Grading-III
Providing, laying, spreading and compacting
crushed graded stone aggregate as per Table
400410 & 400.11 to Wet Mix Macadam
specifications including premixing the Material
with water to OMC in mechanical mixer (Pug
mill) as per design mix, carriage of mixed
Material by tipper to site laying in uniform
layers, with motor grader/F .E, loader/Paver
Finisher, in sub-base/base course on a well
prepared under-base and compacting with
Vibratory Roller to achieve the desired density
including lighting, guarding, barricading and
maintenance of Driversion etc. (MoRTH
specification : Clause 406). with all lead & lift
By mechanical means with lead upto 1 km
Providing and applying primer coat over
prepared surface of granular base with bitumen
émulsion as per 1S:8887 & manufacturer’s
specifications @7 kg/10 sqm with a self
propelled or towed bitumen pressure sprayer
equipped for spraying the Material uniformly at
specified rates and temperatures (including
cleaning of road surface) as per MoRTH
specification : Cl. 502, 112.
8750.00
Providing and applying tack coat on the
prepred surface, with bitumen emulsion as per
9/8887 & manufacturer’s specifications @0.2
kg/sqm with a self propelled or towed bitumen
pressure sprayer equipped for spraying the
Material uniformly at specified rates and
temperatures (including cleaning of road
prea as per MoRTH specification Cl. 502,
12.
4
750.00 ¦ 18750,00
\)
CE Scanned with OKEN Scanner
Providing and applying tack coat on the
preparéd surface, with bitumen cmulsion as per
1S;8887 & manufacturer's Specifications aoa
kg/sqm with a self propelled or towed bit me
pressure sprayer equipped for s
Material uniformly
umen
Praying the
at specified tates and
temperatures (including cleaning of road
surface) as per MoRTH specification Cl, 502
112,
25850.00 assed
@
\ in 204473.50 ¦
~
Providing and laying Bituminous Macadam on
Prepared surface with specified graded crushed
aggregates as per Table 300-7, Grading-2, for
Kase/binding course including loading of
aggregates with F.E. loader and heating &
mixing of stone aggregate and bitumen
(including cost of anti-stripping compound,
wherever required) in hot mix plant (40-60
TPH), transporting the mixed Material in tipper
to paver (sensor as per clause 504.3.5), and
laying mixed Material with paver finisher to the
required level and grade, rolling by power
roller and vibratory compactor as per Cl. 501.6
& 501.7 to achieve the desired density
(approved by the department) excluding cost of
primer/tack coat. [MoRTH Specification :
Clause 504, 112).50/75mm Compacted
thickness with 3.3% bitumen VG30 Grade
Cum
a a an 0.0
Providing and laying open graded premix
carpet 20mm thick (compacted), on prepared
surfagé in a single course as wearing course,
posed of specified graded crushed
agpregates as per Table 500-23, heating
bituminous binder @ 14.6 kg/10 sqm and
aggregates in Hot Mix Plant (including cost of
anti-stripping compound, wherever required),
transporting the mixed Material with tipper and
laying with paver finisher to the required level
and grade, rolling with power roller, 8-10
tonne, but excluding cost of tack coat and seal
coat with all lead and lift. (MoRTH
specification : clause 510, 112) In Hot Mix
Plant 40-60 TPH, including loading of
aggregates with F.E. loader bitumen VG30
grade
ding and applying Premixed Seal Coat
pe comprising of thin application of fine
Aperegate (0.06 cum per 10 sqm) premix with
(6.8 kg per 10 sqm) bitumen binder (including
cost of anti-stripping compound, wherever
required) in mini hot mix plant 6-10 TPH, and
laying with paver finisher and rolling with
power roller 8-10 tonne, including all lead of
mix Material (MoRTH specification : clause
511).Bitumen VG30 grade
94.0 2429900.00
801350.00.
801350.00
CE Scanned with OKEN Scanner
racti construction and
longitudinal joints, joint filler, Separation
membrane, sealant primer, joint sealant, ———
debonding strip, dowel bar, tie rod, aclinistonds
and vacuum processing pump as approved
curing Compound, finishing to lines and grades
as per drawing as per MoRTH Specification :
Clause No. 602, 1 12.Using Cement concrete M
30 pavement Grade
Providing and fixing of precast concrete
interlocking blocks of 80mm thick (M-30
Grade) manufactured from fully computerized
automatic stationery hydraulic vibto perssed
machine & full computerized automatic
batching plant of class A-I as per BS: 6717-
2001. The CC interlocking paving blocks be
laid on average 50mm thick bed of coarse sand
and the joint is to be filled with fine sand.
Laying procedure on compected sub base as
defined. The work includes earth work in
cutting of B/T road, cutting of WBM road and
disposal of unserviceable Material with all
leads & lifts and stacking of serviceable
Material complete job is to be executed as per
the instructions of Engineer-in- charge. The
rates to be inclusive of all lead, lifts & taxes
General specification of Blocks:80mm thick
(M-30 Grade)
Providing and Laying cement concrete 1:4:8 in
sub-base over a prepared sub-grade with coarse
and fine aggregate conforming to 1S:383, the
size of coatse aggregate not exceeding 25mm,
ea cement ratio not to exceed 15:1,
gétregate gradation after blending to be as per
able 600-1, cement content not to be less than
150 kg/cum, optimum moisture content to be
determined during trail length construction,
concrete strength not to be less than 10 Mpa at
7 days, mixed in a batching plant, transported
to site, laid with a paver with electronic sensor,
compacting with 8-10 tonne vibratory roller,
finishing and curing as per MoRTH
specification : Clause No. 601, 112.
patoreed cement concrete M1 5grade
ilometre stone of standard design as per IRC:8
1980, fixing in position including painting and
printing etc,Ordinary kilometer stone (precast)
CE Scanned with OKEN Scanner
Kilometre Stone Reinforced cement concrete
grade kilometre stone of standard design as
per IRC:8-1980, fixing in position including
painting and printing etc Hectometer stone
Boundary pillar.Reinforced cement concrete
M15-grade boundary pillars of standard design
as per IRC:25-1967, fixed in position including
finishing and lettering but excluding painting
Retro-Reflectorised Traffic Signs.Providing
and fixing of retro- reflectorised cautionary,
mandatory and informatory sign as per IRC :67
made of high intensity grade shecting vide
clause 801.3, fixed over aluminium sheeting,
1.5 mm thick supported on a mild steel angle
_\iyon post 75 mm x 75 mm x 6 mm firmly fixed
to the ground by means of properly designed
foundation with M15 grade cement concrete 45
cm x 45 cm x 60 cm, 60 cm below ground level
as per approved drawing .90 cm equilateral
1970.00
No ee
Retro-Reflectorised Traffic Signs Providing
and fixing of retro- reflectorised cautionary,
mandatory and informatory sign as per IRC :67
made of high intensity grade sheeting vide
clause 801.3, fixed over aluminium sheeting,
1.5 mm thick supported on a mild steel angle
iron post 75 mm x 75 mm x 6 mm firmly fixed
to the ground by means of properly designed
foundation with M15 grade cement concrete 45
cm x 45 cm x 60 cm, 60 cm below ground level
as per approved drawing 80 cm x 60 cm
ul No 2185.00
os
Direction and Place Identification Signs upto
0.9 sqm Size Board.Providing and erecting
direction and place identification retro-
reflectorised sign as per IRC:67 made of high
int€nsity grade sheeting vide clause 801.3,
fixed over aluminium sheeting, 2 mm thick
with area not exceeding 0.9 sqm supported on a
mild steel single angle iron post 75 x 75 x 6
mm firmly fixed to the ground by means of .
properly designed foundation with M15 grade
cement concrete 45 x 45 x 60 cm, 60 cm below
ground level as per approved drawing
¦
CE Scanned with OKEN Scanner
mm thick ACP
ack support frame of
angle as approved ,
supported on a mild steel angle iron post 75
mm X75 mm X 6 mn 3 mtr height, firmly
fixed to the pround by means of Properly
designed foundation with M20 grade cement
coticrete 45 em X 45 cm X 60 cm » 60 cm
below ground level as per approved drawing,
10 years Warranty for Retro Reflective
Sheeting from the original sheeting
manufacturer & a certified copy of three years
outdoor exposure report from an independent
test lab for the product offered shall be
submitted by the contractor. (This shall be used
only for N.H, S.H & M.S.H Roads).
Regulatory sign boards of 60 x 50 cm
Rectangle. Size 60 x 50 cms. Rectangle
sheet supported with B
25x25x3mm mild steel
0
Supply of flood gauge (water gauge) as per IRC
67 standard 200cm long fixed on angle iron
posts 50x50x6mm 2.6m long
out or angle iron 50«50x6mm 3m long using
tainless steel nut bolts of 8mm dia aluminium
sheet is covered with high intensity grade Retro
reflective letters in black post duly painted in
black and white synthetic enamel, complete in
all respect confirming to MoRTH specifications
(2001) cl. 801.
hofApplied thermoplastic compound 2.5 mm
ick including reflectorising glass beads @
50 gms per sqm area, thickness of 2.5 mm is
exclusive of surface applied glass beads as per
IRC:35 .The finished surface to be level,
uniform and free from streaks and holes.
CE Scanned with OKEN Scanner
Icro prismat;
capable of providing total thterma ehesiea of
the light entering the lens face and shall sup D0
a load of 16000 kg tested in aecordance O pn
ASTM D 4280 Type H and complying to
Specifications of Category A of MORTH
Ciretlar No RW/NH/33023/10-97 — DO III Dt
M.06. 1997. The height, width and length shall
not exceed 50 mm, 100 mm an
0,00 185.61
+/- 5 degree, The Strength of detachment of the
integrated cylindrical shanks, (of diameter not
less than 19 +/- 2 mm and height not less than
30+/- 2 mm) from the body is to be a minimum
value of 700 Kgf. Fixing will be by drilling
holes on the road for the shanks to go inside,
without nails and using epoxy resin based
adhesive as per manufacturer’s
recommendation and complete as directed by
the engineer, The contractor shall submit 2
years pre qualified warranty certificate from the
manufacturer for satisfactory field performance
Earthwork in excavation for foundation of
structure complete with all lift, dewatering,
shoring and shuttering etc. including refilling
of trenches in 250 mm layer, ramming,
watering and disposal of surplus soil within a
lead of 1000 meters, as per drawing and
technical Earth in excavation for foundation of
speeification. [MoRTH Specification : Clause
304].In ordinary soil [MoRTH Specification :
clause 301].BY MECHANICAL
MEANS. Depth upto 3m
wehs7 700mm da TRow—————*d?SC¦ ea
[sae [000mm GaP? Row ————~id; sr N03
a
Plain Cement Concrete 1:3:6 with 40mm
nominal mix in foundation with crushed stone
aggregate 40mm nominal size mechanically
mixed, placed in foundation and compacted by
¦ vibrator including curing for 14 days. (MoRTH
‘ specification clause : 2100)
silo /
ty = [ {000mm dia HP 1 Row 3038.00 56203,00
See ed 1000mm dia HP 2 Row 3038.00
ma 3038.00 ¦ \ estan
iN
noe
ills
a
Ps
\ .
N
) a
fi :
Providing, laying and spreading of granular sub
base by providing close graded Material,
mixing in a mechanical mix plant at OMC
Carriage of mixed Material to work site,
Spreading in uniform layers with motor grader
On prepared surface and compacting with
vibratory power roller to achieve the desired
density, complete as per clause 401.By Mix in
Place Method.Grading-III
© Scanned with OKEN Scanner
Providing and laying Plain Cement Concrete M
¦
¦
¢/ ¦)
aaa_[ttnm GTP Row [asa ¦ Newer 7
@ ie ¦ 1000mm dia HP 2 Row
15 Mix with stone aggregate 20mm nominal
size mechanically mixed and vibrated, in
superstructure upto 4 meter. above 1.50 m
level from ground/bed level. [MoRTH
Specification : Clause 1000/1700]
EE al
9 3850.00 Saasraszco ¦ to0ez0do_
f) Providing and laying Reinforced cement
’ concrete pipes NP-3 for culverts including
jointing ends and fixing collar with cement on
¦ mortar 1:2. (MoRTH specification : clause
¦ 1000/2900).1000mm dia.
ow 3800_¦
IN
1000mm dia HP 1 Row
OU
0
<
[o)
=
[soon [tin Row ‘ino Sc atomn ¦ 07
iif rao ¦ VCW i
¦ ¦
¦_¦
4410.00 ¦ , 286650.00 220500.00
V
Providing and laying Reinforced cement
concrete pipes NP-3 for culverts including
jointing ends and fixing collar with cement
mortar 1:2. (MoRTH specification : clause
1000/2900).500 mm dia.
S
Ste 20
SE
rrr TSS 29s. BA
- ¦ ____ ¦LessT.P. 15.05% Below as per Tender Primium 4433550.9 g¦ 774364 : a
Teal Value of work done or supplies made to date’4th Running Bill ee OS ee
tedut value of work or supplies shown in provious Paid R.Bill 2082773446 ; —___—
vmuderNo.___Date__ - a =
\etvalue ofwork or supplies since previous bill (F); ~ * SCY 497525.37¦ + Zt
Fie (F) (in Words) RUPEES ssrsscssssvessssesesessnieesecsntnepsbebsissveseesscen a A
ADD With Heald Amount]. X00}
CNN 19752537. 7
sy
PSitsrsssanl 7
ne 0
a ee
! II - CERTIFICATE AND SIGNATURE
(The measurement were made by Vijaypal Katara (JE.) on Dt. 14.06.2025, 15,06.2025) 17.06.20
435-37 of measurment Book No. 1941 ;
» itd by (Name) Mahesh Ahari (A.E.Jon Dated 29.06.2025
+} Mis Certified that \
19.06.2025 & 29.06.2025 and as recorded at
4IATS ——_
1K work done as per PWD/TRG Specification
Bate ae ir agianst the Contractor
‘Wor and as per BSR/agreement
+ Blaby x er sanctioned estimate and as per nominoculture of Sch. G
mitted By Contractor \)
2. Wijay pal Katara) rnkacssoemaeesh Ahariy
Mies West Junior Engineer fh aon La Engineer’
oh. RW, D, SeC. maaan bivision neha WYe Os Sub. Dn. Aspur
ly ee ¦ aVVp of¦ Division B hi
“un pression o Dn. Beneshwar BRADRrep TT nial
Dated Signature of{Rank
Office authorising Pavment
ON Pen eee tee eneseeeeeneececersses
iy Payment
‘Daur ji ym
*Ssary on}
Y When the offi
ite r
er who prepares the bill is not the officer who authorises the payment. In such
Such a case, the tw
; O signature a
re essential,
© Scanned with OKEN Scanner
Ill Memerandum of payment
i mIRRT..& a eel aa a
4 Total value of work done as pef Aggq ei wy ara VIART..S ADT. ;
2 Deduct amount with head ¦
a
7] To Ps ol
w. ape
FIGURES FOR WORK ABSTAGIary _ReTTAT.. soe: ott A er ee Gq
( r]
(a)
From
pee ALY HS. SO. Grn. S28. hort da Our@
* Os.as.42. 04x. dRAe. QS td
coms
a
(b) GIR
From — _ es
this
bill
3 Balanc ¦ up to date payment item (1-1+
4 Total amount of payment
$O.QMN Zu -foy,
already made as per last running 8 6 5 8 Rs as ASS f2er, “LD
account bill No. Vth R.B. Vr
, 0040 Rs. Fp J.Yhayg
5 payment now to be made as dated below ; )
eS Adc
(a) By recovery of . ‘ ~ y
amounts creditable -
to this work
3 LOR FL=L0
(b) By recovery of
amounts creditable
other work or
heads of account
cade cccuseceosccean
(©) By chequs Rs. BO82/25<00 ¦
(d) By case Gross Total A197 >
Total of (b) 5 (a 5
Received Rs. in words cheque
Receive in figure in words
Demand for this work or supplies made
Dated the Left hend thumb impression of &
Re 4 P
Withness of identification and payment Full Signat (fof of Contractor _ q< (
Paid by me Cheque Sateen Dated -------------------- 9
Dated initials of person actully making the payment
The figures should be tested to see that it agree with the total of item 4 and 5
Here specify the net amount payble vide item 5(C) and (D)
The payees acknowledgement should before the grose amount paid item (i.e. a to d)
Amounir
Iwtewy
é
Payment should be attested by sum known person when the Payees acknowledgement is by a mark seal‘or thumb j " )
Not required in the cash of bill suppliers a be eo. we ui iS dire} aftara
The space is resarved for any remarks which the disbursing officer of the Division officer May which record in f
G Scanned with OKEN Scanner