## OCR Content
OCR CONVERTED: New Doc 10-30-2025 14.13.pdf
Converted using Optical Character Recognition
Reference No :55178818
Government Of Rajasthan
jerlou
Month/Year: Jul/2025
Department Code : 65 Department Name : Public Works Department
Detailed Wam bill of : XEN PWD DIV BENESHWAR DHAM (DUNGARPUR)(42908) OfficelD : 42908
Bill For Works Payment: WAM Payment Reference No : 4383689 Wam Reference No : #1/3 of 1287343
Ro Name: XEN PWD DIVISION BENESHWARDHAM HQ Division Code : Bill No : 56178818
UR
Date 1107/2025 DemandNo_ ; ODOCode + 42908
: JDHO02952F Object Head : Budget Head : 5054-04-337-20-01/SFIV
: 3320242.00 NonPlan 2 0. NA : ContigencyHead :
The Treasury/Sub Treasury OfficerASPUR
Please Order to pay % 2157489 as per the claim contained in this bill
Sign of Clerk Sign of DA Sign of Divisional Officer
¦ certified that ¦ have personally examined and satisfied myself about the guinness of claim that the claimed bill is strictly in accordance with rules and that the
Said parties/firm details mentioned in wam bills are correct and said Parties/firm are entitled for such payment and this drawal is within the limites of online allotted
budgeULC.
igned by SHILPA
¦ certified that the compliance of directions/instructions of PWF & AR has been ensured for this bill. bate. 2 028 07.11'20:21:08
Ei 05:30
Sign (With Se: S=Y niignsekign of DDO
9414724969
Bank Name Invoice No. _- Gross Amt
Account No. Invoice Date(In ..» 4-- NetAmt
IFSC Code Case Of _
Branch Name Suppller) ’
MS Shree Bajrang BANK OF BARODA . ssoy > 3320242.00 4383689 0230-00-800-06-00
Construction 15860200000022 = 441411900 2157489.00 24900.00
Village Padli Gujreshwar Post BARBOGENJIX tm) Sy “12:00:00 AM 0853-00-102-01-01
Sansarpur Distt. Dungarpur Pin GENJI, DIST. DUNGARPUR, 74702.00
Code 314404 JRAJASTHAN», ¦ 8443-00-108-00-00
9414724969 “Ss PLA, 599006.00
8443-00-106-00-00
7470.00
8658-00-112-00-00
24900.00
2059-80-001-04-01
235061.00
2059-80-052-04-01
58765.00
3054-03-337-01-03
88148.00
8658-00-139-00-00
49801.00
Gross Amount Rs. 3320242,00 1162753.00
HU,
5; OU
Digital ESign of DDO
No:
Pay @ : 3320242,00
(In Words) : THIRTY THREE LAKH TWENTY THOUSAND TWO HUNDRED
FOURTY TWO ONLY
B.T. Heads ; 1162753.00
Disclaimer : All contents related to this bill are provided by Head of Office/ODO and he/ she Is solely responsible for IL =
SM Courtsey National informatics centre, Rajasthan State Unit (http/paymanager.raj.nic.in) Group Name:5054 Gen Print Date & Time:11/07, tial
G Scanned with OKEN Scanner
Form RPWA 26
GOVERNMENT OF RAJASTHAN
Public Works Department, Jalpur
Bill No.& Date: PayManager Ref. Id(s): 4383689, 4383690, 4383691
Division Name: XEN PWD DIV BENESHWAR DHAM Division Code: 42908
(DUNGARPUR)
WAM Bill Ref No: 129, Dated: 11/07/2025
ACCOUNT BILL
(Referred to in PWF&A Rules 418, 421, 506 and 507)
(Final payments must invariably be made on forms laa on yellow paper which should not be used for intermediate
payments)
[For Contractors — This form Provides for (1) Advance Payment and (2) Payments for measured work. The form of
Account Secured advances, which has been printed separately, should be attached, where necessary]
Work Order Name: Strengthning and Widening of BT Road from Punjpur to Karithdl Khermal road:‘Km.0/00 to 12/00
Vendor Name: MS Shree Bajrang Construction Budget Head: (shown in ‘Debit head / Payment from' table)
Work Order No./ Sanction No.: 1528 Agreement Reference Number: 109/2023-24
Sub Bill No.: 5 Running
Bank IFSC Code: BARBOGENJIX Bank AccountNo.: 15860200000022
Commencement Date: 27/08/2023 Stipulated Completion Date: Actual Completion Date:
27/05/2024
MB Date (Last): 29/06/2025 MB No: 1942 MB Page(s): 34-42
MB Done By: Vijay Pal Katara jen MB Chked By: Mahesh Ahari Aen Inspecting Authority: Shilpa Patidar
Aspur Xen
Photo uploaded (with date): Yes, 21/06/2025 Physical Progress completion stage: 34 %
ree
ACCOUNT OF WORK EXECUTED a
Items of work Rate Quantity executed as per Payment on the basis of Remarks
(grouped Measurement Book actual measurements
under sub-
heads" of
estimate)
Since
previous bill
Up to date
¦
¦
¦
{As per enclosed bill (Physical) No. & Date, Amount as Per pass order of the bill)
1 Total value of work done to date (A): 2,50,25,259 —
¦2. Deduct value of work shown on previous bill: 20827734
3. Net value of work current bill (1-2=3) (F):4197525 =
Figure e (F) ( in words): Rupees Forty One ¦ Lakh Ninety Seven Thousand 1 Five Hundreds Twenty Five Only
Courtesy: hitps://wam.rajasthan.gov.in (Printed on 7/11/2025 2:01:17 PM)
G Scanned with OKEN Scanner
fied that :
has actually been done in connection
. In addition to and quite from the quantities of work actually executed, as shown in column 4 of Account, some work
with several items and the value of such work (after: deduction there from the
proportionate amount of secured advances, if any, ultimately recoverable on account of the quantities of materials
used therein) is in no case, less than t
he advance payment as per item 2 of the Memorandum if payments made or
proposed to be made, for the convenience of the contractor, In anticipation of and subject to the result of detailed
measurements, which will be made as soon as possible.
2. The Work has been done as per Specifications, Contract Agreement & Drawings found satisfactory.
3. Nothing is outstanding against Contractor regarding this work.
4. No tools & Plants has been issued to the Contractor.
5. Material has been used by Contractor as per Specifications.
6. The Payment of this bill is not drawn previously.
7, Bank Details of the Contractor/Supplier has been checked & verified.
8, All formalities & observations regarding necessary entries are personally examined.
ment from:
H de
37-20-01-74-V-
2 Workld: 214297
f
5054-04-789-05-00-74-V-P
D
eductions / Recoveries:
_— : om =n
NN} OO} al] &] wl] hy! =F
8443-00-106-00-00
8443-00-108-00-00
0853-00-102-01-01
0230-00-800-06-00 88872
-eaazan0800-00
8658-00-112-00-00 P8872
8658-00-139-00-00
D Account (DMFT)
unt es
oi
[o}
So
ao
So
oO
oO
oO
mo}
fe)
n
a.
1
s
a
-—_
=
¦ 0
An
a
pane
fee)
h
rt
wo
2
Labour Welfare ¦
Deposit-Il (SD2) (8443) ¦
Income Tax : ¦
71144] GSTIN Deduction ¦
This Bill will break in following part
EY Ret No: ee 1 a ee 5
~ 4383689
8658-00-139-C0-00
8443-00-108-00-00
8658-00-1 12-00-00
0230-00-800-06-00
0853-00-102-01-01
8443-00-106-00-00
443-00-108-00-00
8443-00-108-00-00
5054-04-337-20-01-74-V-P
Payment Through Treasury
5054-04-337-20-01-74-V-P
2059-80-001-04-01-98-V-P
2059-80-052-04-01-98-V-
P
3054-03-337-01-03-98-V-P
[4383690 5054-04-796-07-00-74-V-P_
8658-00-139-00-00
(s) for PayManager (Fisrt column will be RefNo to pull it on PayManager)
3 .s n pe
2938268
49801
249006
24900
Rr
¦
a
1
¦
{
i
381974! Prorata Workld:
214297
545678] Workld: 214297 ;
Courtesy: https://wam.rajasthan.gov.in (Printed on 7/1 1/2025 2:01:17 PM)
il
G Scanned with OKEN Scanner
0230-00-800-06- ————______
00-800-06-00 4624
0853-00-102-07-04 13873
8443-00-106-00-00 1387 7
8443-00-14 08-00-00 ‘465000 ;
Payment Through Treasury 400677
Oe ene A
5054-04-796-07-00-74.V-p 70938] Prorata Workld:
{ ¦ ¦ 214297
¦ ¦ 2059-80-001 -04-01-98-\V-p 43654 Prorata
¦ . 2059-80-052-04-01-98.\-p 10914] Prorata
Ieee RE 10014
3054-03-337-01-03-98-v-P tes7o, Prorata
4383691 5054-04-789-05-00-74-\-_p ¦ 7713679) Workld: 214297
8443-G0-108-00-00
8658-00-112-00-
0230-00-800-06-00
0853-00-102-01-01
8443-00-106-00-00
8443-00-108-00-
Payment Through Treasury
5054-04-789-05-00-74.V-P
¦
]
¦ ¦
Prorata Workld: ¦
; 214297 ¦
2059-80-001-04-04 -98-V-P
¦ 2059-80-052-04-01-98.V_P Prorata
3054-03-337-01-03-98.\-P : 21407 Prorata ¦
eee 21407 —_ a
Net Amount Payable In Figures: 3082125
(In Words): Rupees Thirty Lakh Eighty Two Thousand One Hundreds Twenty Five Only
Dated
Foru isiorial Office
(fren orétere)
oHPRPRANTe AR Qu seal
——¦___Ghipsetettaceres nba cia)
are arg, , . 9
Courtesy; https://wam.rajasthan.gov.in (Printed on 7/11/2025 2:01:17 PM)
G Scanned with OKEN Scanner
. Bill Submitted By the Contractor
Dn. Beneshwar Dham Vr. No.___ Date RPWA From No, 26 & 27B
Referred to PWF & A Rules 418, 421,506 & 507
Final Payment must invariably be made on form printed on yellow Paper which should not be used for Intermediate payment
(for contractor & suppliers only for payments for work or supplies actually measured)
Vth Running ACCOUNT BILL
Cash Book Voucher No Dated ssa essen
Name of contractor or supplier Bajrang Construction
Name of work
Strengthing and Widening of BT Road from Punjpur Kanthadi Khermal Km 0/0 to 42/0.
Serial No. of this Bill : 1Vth Running Bill and date of the previous bill for this work + IHIrd Running Bill
Reference to Work order & Aggreement No. 1528/17-08-2023 Ag. No. 109/2023-24
Date of written order to commence work : 27-08-2023 Stipudate date of completion : 27-05-2024
Date of actual completion of work: WIP Date of Mesurment: 14.06.2025, 15,06.2025, 17.06.2025, 19.06.2025 &
29.06.2025
Item of work supplies
(grouped under "Sub-heads”
& "Sub-works” of estimate)
% Since Provisional bill (Total
Up-to-date for each sub head)
QD
a a
yA 534724.06 Q
‘CUTED OR
uprooting rank vegetation, grass, brush, shrubs,
saps and trees of girth upto 300mm,
erhoval of stumps, disposal of unserviceable
aterial and stacking of serviceable Material
upto 1000m from road boundary. (MoRTH
Specification : Clause 201).BY
MECHANICAL MEANSIn area of Light
Jungls:
Eafthwork in excavation for roadway in soil,
ncluding stacking / disposal of surplus
Material exclusive of compensation of earth.
(MoRTH specification : clause 301 to 305).By
Hydraulic Excavator CK-90 of 0.9 cum bucket
capacity and tipper with disposal upto 1000
ork in excavation in ordinary rock,
luding stacking / disposal of surplus
Material exclusive of compensation of earth.
(MoRTH specification ; clause 301 to 305).By f on
Hydraulic Excavator CK-90 of 0.9 cum bucket
/
capacity and tipper with disposal upto 1000
mtrs.
Earthwork in excavation for roadway in hard —
6ck, including stacking / disposal of surplus
Material exclusive of compensation of earth.
(MoRTH specification : clause 391 to
305).Blasting prohibited.By Mechanica’
0
sat obtained from borrow-pits with all
ffs and leads, transporting to site, spreading,
grading to required slope and compacting by
vibratory roller 8-10 tonne to meet requirement
of Table 300-2 including cost of compensation
for earth taken from private land with lead upto
1 km as per MoRTH Specification : Clause No.
305.
/
392740.24
G Scanned with OKEN Scanner
Construction of embankment with approved
Materials deposited at site from roadway
cutting and excavation from drain and
foundation of other structures graded and
compacted by vibratory roller 8-10 tonne to
meet requirement of Tale 300-2 as per MoRTH
specification : Clause No. 305
i}
from borrow-pits with all lifts and leads,
8.00 od transporting to site, spreading, grading to
: require slope and compacted by vibratory roller
8-10 tonne to meet requirement of Table 300-2
¦ as per MoRTH specification : Clause No, 305.
Providing, laying and spreading of granular sub
base by providing close graded Material,
mixing in a mechanical mix plant at OMC
carriage of mixed Material to work site,
spreading in uniform layers with motor grader
on prepared surface and compacting with
vibratory power roller to achieve the desired
density, complete as per clause 401. By Mix in
Place Method Grading-III
Providing, laying, spreading and compacting
crushed graded stone aggregate as per Table
400210 & 400.11 to Wet Mix Macadam
Patt including premixing the Material
with water to OMC in mechanical mixer (Pug
mill) as per design mix, carriage of mixed
Material by tipper to site laying in uniform
layers, with motor grader/F.E. loader/Paver
Finisher, in sub-base/base course on a well
prepared under-base and compacting with
\ Vibratory Roller to achieve the desired density
¦ including lighting, guarding, barricading and
10.00
specific
By mechanical means with lead upto 1 km
Providing and applying primer coat over
vara surface of granular base with bitumen
¢ulsion as per 1S:8887 & manufacturer’s
specifications @7 kg/10 sqm with a self
propelled or towed bitumen pressure sprayer
equipped for spraying the Material uniformly at
\specified rates and temperatures (including ~~
cleaning of road surface) as per MoRTH
specification : Cl, 502, 112.
8750.00
rovidifig and applying tack coat on the
4red surface, with bitumen emulsion as per
93887 & manufacturer’s specifications @0.2
; kg/sqm with a self propelled or towed bitumen
pressure sprayer equipped for spraying the oe ~~, YO
-8750,00 ¦ 18750.00 ¦Material uniformly at specified rates and - 148342.50 -69212
temperatures (including cleaning of road rs
surface) as per MoRTH specification Cl. 502, ,
112,
G Scanned with OKEN Scanner
¦
}
¦
-
14.00
/
25950.00
providing and applyin
pgs ais with bitumen emulsion as per
1S:8887 & manufacturer’s specifications @0.2
cé/sqm with a self propelled or towed bitumen
pressure sprayer equipped for spraying the
Y ¦\Material uniformly at specified rates and
temperatures (including cleaning of road
surface) as per MoRTH specification cl. 502,
thickness with
specification :
grade
f
d surface with specified graded crushed
mixing of stone aggregate and bitumen
(including cost of anti-stripping compound,
wherever required) in hot mix plant (40-60
TPH), transporting the mixed Material in tipper
(approved by the
primer/tack coat. [MoRTH Specification H
Clause 504, 112].50/75mm Compacted
Providing and ¦
carpet 20mm thick (compacted), on prepared
surfagé in a single course as wearing course,
co Cased of specified graded crushed
odors as per Table 500-23, heating
ituminous binder @ 146 ke/10 sqm and
aggregates in Hot Mix Plant (including cost of
anti-stripping compound, wherever required),
transporting the mixed Material with tipper and
laying with paver finisher to the required level
and grade, rolling with power roller, 8-10
tonne, but excluding cost of tack coat and seal
coat with all lead and lift. (MoRTH
Plant 40-60 TPH, including loading of
aggregates with F.E, loader bitumen VG30
g tack coat on the
g Bituminous Macadam on
and
3.3% bitumen VG30 Grade
aying open graded premix
clause 510, 112) In Hot Mix
xed Seal Coat
ty plication of fine
d premix with
25850.00 p equired) in mini hot
laying with paver finisher and rolling with eg
: power roller 8-10 tonne, including all lead of
mix Material (MoRTH specification : clause
§11).Bitumen VG30 grade ,
~~
/ Va
2429
801350.0
© Scanned with OKEN Scanner
f)
Providing and Laying un-reinforced, dowel
jointed, plain cement concrete pavement over a
prepared sub-base with 43 grade cement, coarse
and fine aggregate conforming to 1S:383,
maximum size of coarse aggregate not
exceeding 25mm, mixed in a batching and
mixing plant as per approved mix design,
transported to site, laid with a fixed form or slip
form paver, spread, compacted and finished in
aContinuous operation including provision of >
contraction, expansion, construction and 4600.00 Py ari
longitudinal joints, joint filler, separation
membrane, scalant primer, joint scalant, —
debonding strip, dowel bar, tic rod, admixtures ¦ P
and vacuum processing pump as approved,
curing compound, finishing to lines and grades
as per drawing as per MoRTH Specification :
Clause No. 602, 112.Using Cement concrete M
30 pavement Grade
Providing and fixing of precast concrete
interlocking blocks of 80mm thick (M-30
Grade) manufactured from fully computerized
automatic stationery hydraulic vibto perssed
machine & full computerized automatic
batching plant of class A-I as per BS: 67 17-
2001. The CC interlocking paving blocks be
laid on average 50mm thick bed of coarse sand
and the joint is to be filled with fine sand.
Laying procedure on compected sub base as
defined. The work includes earth work in
cutting of B/T road, cutting of WBM road and
disposal of unserviceable Material with all
leads & lifts and stacking of serviceable
Material complete job is to be executed as per
the instructions of Engineer-in- charge. The
rates to be inclusive of all lead, lifts & taxes
General specification of Blocks:80mm thick
(M-30 Grade)
18.00
Providing and Laying cement concrete 1:4:8 in
sub-base over a prepared sub-grade with coarse
and fine aggregate conforming to IS:383, the
size of coarse aggregate not exceeding 25mm,
ager gate cement ratio not to exceed 15:1,
gsregate gradation after blending to be as per
able 600-1, cement content not to be less than
150 kg/cum, optimum moisture content to be
determined during trail length construction,
concrete strength not to be less than 10 Mpa at
7 days, mixed in a batching plant, transported
to site, laid with a paver with electronic sensor,
compacting with 8-10 tonne vibratory roller,
finishing and curing as per MoRTH
specification : Clause No. 601, 112.
19.00
Z _
pemnforeed cement concrete M1 5grade
l ilometre stone of standard design as per IRC:8
0.00 1980, fixing in position including painting and
printing etc,Ordinary kilometer stone (precast)
Oa aaaiaieaie ee tant eee
Qa a
rl
G Scanned with OKEN Scanner
>
f ¦ ae
Kilometre Stone Reinforced cement concrete
MdSerade kilometre stone of standard design as
per IRC:8-1980, fixing in position including
painting and printing etc Hectometer stone
(precast)
Boundary pillar. Reinforced cement concrete
Mis grade boundary pillars of standard design
as per IRC:25-1967, fixed in position including
finishing and lettering but excluding painting
0.00 Va
Retro-Reflectorised Traffic Signs,Providing
and fixing of retro: reflectorised cautionary,
mandatory and informatory sign as per IRC :67
made of high intensity grade sheeting vide
clause 801.3, fixed over aluminium shecting,
1.5 mm thick ‘supported on a mild steel angle
iron post 75 mm x 75 mm x 6 mm firmly fixed
to the ground by means of properly designed
foundation with M15 grade cement conerete 45
cm x 45 cm x 60 cm, 60 cm below ground level
as per approved drawing .90 cm equilateral
triangle
++
7 Fo
MRetro-Reflectorised Traffic Signs Providing
and fixing of retro- reflectorised cautionary,
mandatory and informatory sign as per IRC :67
made of high intensity grade sheeting vide
clause 801.3, fixed over aluminium sheeting,
15 thick supported on a mild steel angle
iron post 75 mm x 75 mm x 6 mm firmly fixed
to the ground by means of properly designed
foundation with M15 grade cement concrete 45
cm x 45 cm x 60 cm, 60 cm below ground level
as per approved drawing 80 cm x 60 cm
rectangular
Direction and Place Identification Signs upto
0.9 sqm Size Board.Providing and erecting
direction and place identification retro-
reflectorised sign as per IRC:67 made of high
inténsity grade sheeting vide clause 801.3,
fixed over aluminium sheeting, 2 mm thick
with area not exceeding 0.9 sqm supported on a
mifd steel single angle iron post 75 x 75 x 6
mm firmly fixed to the ground by means of .
properly designed foundation with M15 grade
cement concrete 45 x 45 x 60 cm, 60 cm below
ground level as per approved drawing
25.00
G Scanned with OKEN Scanner
Providing and Fixing of Retro Reflectorised
600 x 500 mm Chevro sign boards made out of
retro reflective sheeting of micro prismatic
grade conforming to IRC-67: 2082 & TypeXI
standards of ASTM D4956-09 specifications,
fixed over 2 mm thick Al /4mm thick ACP
sheet supported with Back support frame of
25x25x3mm mild steel angle as approved ,
supported on a mild steel angle iron post 75
mm.X 75 mm X 6 mm - 3 mtr height, firmly
fixed to the ground by means of properly
ae coca tal with M20 grade cement
coricrete 45 cm X 45 cm X 60 cm, 60 cm
below ground level as per approved drawing.
10 years Warranty for Retro Reflective
Sheeting from the original sheeting
manufacturer & a certified copy of three years
outdoor exposure report from an independent
test lab for the product offered shall be
!submitted by the contractor. (This shall be used
only for N.H, S.H & M.S.H Roads).
Regulatory sign boards of 60 x 50 cm
Rectangle. Size 60 x 50 cms. Rectangle
26.00) No
—
Supply of flood gauge (water gauge) as per IRC
67 standard 200cm long fixed on angle iron
posts 50x50x6mm 2.6m long
upply of retro-reflective name board size
28.00
black and white synthetic enamel, complete in
all respect confirming to MoRTH specifications
¦ (2001) cl. 801.
ith Hot Applied Thermoplastic
dwith Reflectorising Glass Beads on
ick including reflectorising glass beads @
50 gms per sqm area, thickness of 2.5 mm is
G Scanned with OKEN Scanner
Earthwork in excavation for foundation of
structure complete with all lift, dewatering,
shoring and shuttering etc. including refilling
of trenches in 250 mm layer, ramming,
watering and disposal of surplus soil within a
lead of 1000 meters, as per drawing and
}technical Earth in excavation for foundation of
specification. [MoRTH Specification : Clause
4].In ordinary soil [MoRTH Specification :
/ \yes 301].BY MECHANICAL
ANS.Depth upto 3m
woe iets toe
aad
Raised Pavment Marker ( Cats Eyes);
Supplying and Fixing of Molded Shank
Raised Pavement Markers made of
polycarbonate and ABS moulded body and
reflective pancls with micro prismatic lens
capable of providing total internal reflection of
the light entering the lens face and shall support
a load of 16000 kg tested in accordance to
ASTM D 4280 Type H and complying to
Speci wk cations of Category A of MORTH
Cirgtil ar No RW/NH/33023/10-97 — DO III Dt
4.06, 1997. The height, width and length shall
not exceed 50 mm, 100 mm and 100 mm and
with minimum reflective area of 13 Sqcm on
each side and the slope to the base shall be 35
+/- 5 degree. The strength of detachment of the
integrated cylindrical shanks, (of diameter not
less than 19 +/- 2 mm and height not less than
30+/- 2 mm) from the body is to be a minimum
value of 700 Kef. Fixing will be by drilling
holes on the road for the shanks to go inside,
without nails and using epoxy resin based
adhesive as per manufacturer’s
recommendation and complete as directed by
the engineer. The contractor shall submit 2
years pre qualified warranty certificate from the
manufacturer for satisfactory field performance
. t
Katdam daPTRow ¦ sta ¦ tessa ¦ 0007” 7
—— —— ers
PS sae [ome 7
o
Pafaa¦ | [ ieee a
: in
alas ee ¦ as/
3.00 cum a a ae fem af ah
Se ee [eae er] sre ¦ Sree [a
Plain Cement Concrete 1:3:6 with 40mm
nominal mix in foundation with crushed stone
aggregate 40mm nominal size mechanically
mixed, placed in foundation and compacted by
vibrator including curing for 14 days. (MoRTH
icatice clause : 2100)
aT ¦ ae
Providing, laying and spreading of granular sub
base by providing close graded Material,
mixing in a mechanical mix plant at OMC
carriage of mixed Material to work site,
40.00 spreading in uniform layers with motor grader 0.00
on prepared surface and compacting with
vibratory power roller to achieve the desired
density, complete as per clause 401.By Mix in
Place Method.Grading-III
G Scanned with OKEN Scanner
ee ee
Providing and laying Plain Cement-Conerete M
15 Mix with stone Aggregate. 20mm nominal’, }
r size mechanically mixed and vibrated, in.
\¦superstruictute upto 4imeter “above 1.50 m ~
level from ground/bed level. [MoRTH
Specification : Clause 1000/1700) ~~
3950.00
:
Providing and laying
: \ concrete pipes NP-3'for culverts including
\ {jointing ends and fixing collar with cement
mortar 1:2. (MoRTH specification : clause”
1000/2900).1000mm dia.
7
Tam[ Ror ome [see [00OnmEaAFT ROW aoa SY
000 [ttn ia Row aainor ¦ Nasco [000 7
_ y
49,00
YN Providing and laying Reinforced cement
concrete pipes NP-3 for culverts including
jointing ends and fixing collar with cement
mortar 1:2. (MoRTH specification : clause
eacsis aah 1000/2900).500 mm dia. q ZL
spatial spo L ne ilo 00 tenon Yo 7
Se Se Aaa 77S SSE CTE
PN 44335509977 743646341 ”
[—_¦.___¦Less T.P. 15.05% Below as per TenderPrimium ¦ i
P¦ 82502525988
™
¦ S20827734336)
Xd
¦. sTotal Value of work done or supplies made to date 4th Running Bill
Dedutt value ofwork or supplies shown in provious Paid R.Bill
Ik
“\, Voucher No: >Date _____ r
~ _Netvalue of work orsupplies since previous bill (F): ~ * a Neto7sasa7] 7
YS -TBigute (RJ Git Words) Rupees ssrssseneeaseseernse stenotic: Totti
ADD With Heald Amoun SS 1 ):)
_ PN 975253377 7
ne
_ ng Ya
AsperAllocationl ¦ St—<“~dSSSC~C‘C;~S~dC‘SCT
- ae Il - CERTIFICATE AND SIGNATURE
\, .(1). The measurement were imade‘by:Vijaypal Katara (JE.) onpt 14.06:2025, 15,06.2025) 17.06.20
page 35-37 of measurment Book No. 1941 a :
Checked by (Name) Mahesh ‘Ahari (A.E.)on Dated 29.06.2025. ¦
(2). Itis Certified that
1. The work done as per PWD/TRG Specification
19,06.2025 & 29.06.2025 ant as recorded at
447 S25/-—
2, Nothing out standing’agianst the Contractor
3. Rate allowed and as per-BSR/agreement
4. Work done as per sanctioned estimate and as per nominoculture of Sch. G
5. Bill Submitted By Contractor, ‘ M a esh Ah —
t a ete C0 Fo aya. =¦
¦ <4 an £4 4 (Vifay al Katara) _ ¦Rank Assistant Engineer J a riy
ware Gy PAY:
Ge eae —— Junior Engineer sub division MBANStANt Engineer‘
ale _ , _ PoWe D, Sec. Cane aes Division eth Os SUD. Dn. Aspur
Pp
eR "Dp Beneshwar Ohi
Dated Signature Of[RANK srsssessersvsseseenesseaeosens "0
Office authorising Pavment
Payment!
‘This Signature Is necessary only when the officer who prepares the bill is not the officer who authorises the payment. In such a case, the two signature are essential.
. signature are essential.
© Scanned with OKEN Scanner
4 Total value of work done as pe}
2 Deduct amount with head
FIGURES FOR WORK ABSTHAG:
AdGAtrie
ill Memerandum of payment
ft &y uta a2 A,
(a) Les - of] . a ISS}, 4
From R.BE LLL See AA Sor A ard
previe ~ av
us bill C1)
$4
a: ~
= | @
last
bill ra)
(b)
From
this
Va. GER
Kael
bil
3 Balanc ¦ up to date payment item (1- “+
4 Total amount of payment
already made as per last tunning
account bill No. Vth R.B. Vr
No
Mes-4
5 payment now to be made as dated below
Total of (b) 5 (a
Received Rs. in words
cheque
Receive in figure in words Amou
Demand for this work or supplies made
Dated the Left hend thumb impression of
Withness of identification and payment —: Full Signat
Paid by me Cheque No}--------—------------ Dated ---------------
cSraaseceese aeete
Gress Yn 22 “feet DOr)
LEQ — Aha
foot of 30 8 24{2S5=to
awnnn=n== Q) book entry dated
II CE
ae eam
2S. SUD
O.Q0uy FO,
8658 Rs..¦ 75S acu, “A
0040 Rs. 7 ).Y4:
(a) By recovery of ‘ 0230 Rs.. 2SSS7 hee)
tottiswork 0853 Rs..1.L0.67/ 72D
b) B f ~ LOGFQ-0
sereiae peaetie 0059 Rs... NaEweunes a
otherworkor Pp Stamp «6¦l OOBS Rs...
heads of account ” Rs ly We / fa) O ra BG
(c) By chequs
(d) By case Gross Total
s RSE ZALS“U
EYLABOO PA
Tat initials of persoractuel
/
Dated US of person actully Se the payment
The figures should be tested to see that it agree with the total of item 4 and 5
Here specify the net amount payble vide item 5(C) and (D)
The payees acknowledgement should before the grose amount paid item (i.e. a to d)
Payment should be attested by sum known person when the payees acknowledgement is by a mark seal'cr thumb S
S )
Not required in the cash of bill suppliers. bu ot aferen
ac? “yd p
The space is resarved for any remarks which the disbursing officer of the Division Officer may whieh record in ra
G Scanned with OKEN Scanner