## PDF Content
Converted from: RETWALL BILL.pdf
--- PAGE 1 ---
1 | 1EarthworkinexcavationforfoundationofB-1 structure complete with all lift, dewatering, 1.1.4 shoring and shuttering etc. including refilling of trenches in 250 mm layer, ramming, watering and disposal of surplus soll within a lead of 1000 meters, as per drawing and technical Earth In excavation for foundation of specification. [MORTH Specification: Clause 304]. in ordinary soll [MORTH Specification clause 301] BY MECHANICAL MEANS Depth upto 3m | 935.74 | Cum | 57 | P Cum | 53337.32
2 | Earthwork In excavation for foundation of B-1 structure complete with all lift, dewatering, 1.3.2 shoring and shuttering etc. including refilling of trenches in 250 mm layer, ramming, watering and disposal of surplus soil within a lead of 1000 meters, as per drawing and technical Earth in excavation for foundation of specification. [MORTH Specification Clause 304].In Ordinary/Soft rock (not requiring blasting) [MORTH Specification: Clause 3011 BY MECHANICAL MEANS | 382.44 | Cum | 83 | P Cum | 31742.51
3 | Structural cement concrete (Design Mix) in open foundations, with form work, at level. Cement concrete for plain/reinforced concrete in open foundations as per drawing and technical specification. [MORTH Specification: Section 1700 & 1500). With 20mm nominal size aggregate P.C.C. M-15 grade | 93.57 | Cum | 3038 | P Cum | 284278.57
4 | Structural cement concrete for plain concrete/ reinforced concrete for substructure at any level, complete as per [MORTH Specification: Section 1500 & 1700]. drawing and technical specification. Design mix concrete PCC M-15 Upto 5 mtr. Height | 1863.99 | cum | 3666 | P Cum | 6833377.26
6 | Providing A.C. pipe Weep holes 150mm B-3 dia in Masonry/plain Concrete/Reinforced 13 Concrete abutment, wing wall/return wall complete as per drawing and technical specification. [MORTH Specification : Clause 2205]. | 489.60 | R mtr | 114 | P RM | 55814.40
--- PAGE 2 ---
RETAINING WALLS (PADLI GUJARESHWAR)
DETAILS OF MEASUREMENTS
S.N. Particulars Nos. Length Breadth Height Qty. Units
1 Earthwork in excavation for foundation of
structure complete with all lift, dewatering,
1.1.4 shoring and shuttering etc. including
refilling of trenches in 250 mm layer,
ramming, watering and disposal of surplus
soll within a lead of 1000 meters, as per
drawing and technical Earth In excavation
for foundation of specification. [MORTH
Specification: Clause 304]. in ordinary soll
[MORTH Specification clause 301] BY
MECHANICAL MEANS Depth upto 3m
Return Walls 1 1 x 15 x 2.22 x 1.50 = 49.88 Cum
1 x 15 x 2.77 x 1.50 = 62.25 Cum
1 x 15 x 2.73 x 1.50 = 61.50 Cum
1 x 15 x 2.63 x 1.50 = 59.25 Cum
1 x 15 x 2.68 x 1.50 = 60.38 Cum
1 x 15 x 2.67 x 1.50 = 60.00 Cum
1 x 15 x 2.60 x 1.50 = 58.50 Cum
1 x 15 x 2.52 x 1.50 = 56.63 Cum
1 x 15 x 2.65 x 1.50 = 59.63 Cum
1 x 15 x 2.68 x 1.50 = 60.38 Cum
1 x 2 x 2.68 x 1.50 = 8.05 Cum
Return Walls 2 1 x 15 x 2.42 x 1.50 = 54.38 Cum
1 x 15 x 2.33 x 1.50 = 52.50 Cum
1 x 7 x 2.12 x 1.50 = 22.23 Cum
1 x 15 x 2.28 x 1.50 = 51.38 Cum
1 x 15 x 2.27 x 1.50 = 51.00 Cum
Return Walls 3 1 x 6.95 x 2.27 x 1.50 = 23.63 Cum
Return Walls 4 1 x 6.9 x 2.68 x 1.50 = 27.77 Cum
Pipe Culvert 1 x 6.2 x 2.77 x 1.50 = 25.73 Cum
Pipe Culvert 1 x 7.4 x 2.77 x 1.50 = 30.71 Cum
Total Qty. 935.74 Cum
2 Earthwork Inexcavation for foundation of B-
1 structure complete with all lift, dewatering,
1.3.2 shoring and shuttering etc. including
refilling of trenches in 250 mm layer,
ramming, watering and disposal of surplus
soil within a lead of 1000 meters, as per
drawing and technical Earth in excavation
for foundation of specification. [MORTH
Specification Clause 304].In Ordinary/Soft
rock (not requiring blasting) [MORTH
Specification: Clause 3011 BY
MECHANICAL MEANS
Return Walls 1 1 x 15 x 2.22 x 0.45 = 14.96 Cum
1 x 15 x 2.77 x 0.50 = 20.75 Cum
1 x 15 x 2.73 x 1.25 = 51.25 Cum
1 x 15 x 2.63 x 1.90 = 75.05 Cum
1 x 15 x 2.68 x 0.90 = 36.23 Cum
1 x 15 x 2.67 x 0.45 = 18.00 Cum
--- PAGE 3 ---
S.N. Particulars Nos. Length Breadth Height Qty. Units
1 x 15 x 2.60 x 0.60 = 23.40 Cum
1 x 15 x 2.52 x 0.75 = 28.31 Cum
1 x 15 x 2.65 x 0.25 = 9.94 Cum
1 x 15 x 2.68 x 0.35 = 14.09 Cum
1 x 2 x 2.68 x 0.35 = 1.88 Cum
Return Walls 2 1 x 15 x 2.42 x 0.30 = 10.88 Cum
1 x 15 x 2.33 x 0.35 = 12.25 Cum
1 x 7 x 2.12 x 0.35 = 5.19 Cum
1 x 15 x 2.28 x 0.35 = 11.99 Cum
1 x 15 x 2.27 x 0.35 = 11.90 Cum
Return Walls 3 1 x 6.95 x 2.27 x 0.45 = 7.09 Cum
Return Walls 4 1 x 6.9 x 2.68 x 0.50 = 9.26 Cum
Pipe Culvert 1 x 6.2 x 2.77 x 0.50 = 8.58 Cum
Pipe Culvert 1 x 7.4 x 2.77 x 0.56 = 11.47 Cum
Total Qty. 382.44 Cum
3 Structural cement concrete (Design Mix) in
open foundations, with form work, at level.
Cement concrete for plain/reinforced
concreteinopenfoundationsasperdrawing
and technical specification. [MORTH
Specification:
Section 1700 & 1500).
With 20mm nominal size aggregate
P.C.C. M-15 grade
Return Walls 1 1 x 15 x 2.22 x 0.15 = 4.99 Cum
1 x 15 x 2.77 x 0.15 = 6.23 Cum
1 x 15 x 2.73 x 0.15 = 6.15 Cum
1 x 15 x 2.63 x 0.15 = 5.93 Cum
1 x 15 x 2.68 x 0.15 = 6.04 Cum
1 x 15 x 2.67 x 0.15 = 6.00 Cum
1 x 15 x 2.60 x 0.15 = 5.85 Cum
1 x 15 x 2.52 x 0.15 = 5.66 Cum
1 x 15 x 2.65 x 0.15 = 5.96 Cum
1 x 15 x 2.68 x 0.15 = 6.04 Cum
1 x 2 x 2.68 x 0.15 = 0.81 Cum
Return Walls 2 1 x 15 x 2.42 x 0.15 = 5.44 Cum
1 x 15 x 2.33 x 0.15 = 5.25 Cum
1 x 7 x 2.12 x 0.15 = 2.22 Cum
1 x 15 x 2.28 x 0.15 = 5.14 Cum
1 x 15 x 2.27 x 0.15 = 5.10 Cum
Return Walls 3 1 x 6.95 x 2.27 x 0.15 = 2.36 Cum
Return Walls 4 1 x 6.9 x 2.68 x 0.15 = 2.78 Cum
Pipe Culvert 1 x 6.2 x 2.77 x 0.15 = 2.57 Cum
Pipe Culvert 1 x 7.4 x 2.77 x 0.15 = 3.07 Cum
Total Qty. 93.57 Cum
--- PAGE 4 ---
S.N. Particulars Nos. Length Breadth Height Qty. Units
4 Structural cement concrete for plain
concrete/ reinforced concrete for
substructure at any level, complete as per
[MORTH Specification: Section 1500 &
1700]. drawing and technical specification.
Designmixconcrete PCCM-15Upto5mtr.
Height
Return Walls 1 1 x 15 x 1.92 x 2.9 = 83.38 Cum
1 x 15 x 2.47 x 4.1 = 151.70 Cum
1 x 15 x 2.43 x 4.3 = 156.95 Cum
1 x 15 x 2.33 x 4.3 = 150.50 Cum
1 x 15 x 2.38 x 4.3 = 153.73 Cum
1 x 15 x 2.37 x 4.25 = 150.88 Cum
1 x 15 x 2.30 x 4.35 = 150.08 Cum
1 x 15 x 2.22 x 4.1 = 136.33 Cum
1 x 15 x 2.35 x 4.2 = 148.05 Cum
1 x 15 x 2.38 x 4.3 = 153.73 Cum
1 x 2 x 2.38 x 4.3 = 20.50 Cum
Return Walls 2 1 x 15 x 2.12 x 2.90 = 92.08 Cum
1 x 15 x 2.03 x 2.95 = 89.98 Cum
1 x 7 x 1.82 x 2.60 = 33.06 Cum
1 x 15 x 1.98 x 2.95 = 87.76 Cum
1 x 15 x 1.97 x 2.90 = 85.55 Cum
Return Walls 3 1 x 6.95 x 4.6 x 0.15 = 4.80 Cum
Return Walls 4 1 x 6.9 x 4.85 x 0.15 = 5.02 Cum
Pipe Culvert 1 x 6.2 x 4.85 x 0.15 = 4.51 Cum
Pipe Culvert 1 x 7.4 x 4.9 x 0.15 = 5.44 Cum
Total Qty. 1863.99 Cum
5 Providing A.C. pipe Weep holes 150mm B-
3 dia in Masonry/plain Concrete/Reinforced
13 Concrete abutment, wing wall/return wall
complete as per drawing and technical
specification. [MORTH Specification :
Clause 2205].
Return Walls 1 1 x 102 x 1.10 = 112.20 RM
1 x 102 x 1.60 = 163.20 RM
Return Walls 2 1 x 46 x 1.10 = 50.60 RM
1 x 46 x 1.60 = 73.60 RM
Return Walls 3 1 x 6 x 1.10 = 6.60 RM
1 x 6 x 1.60 = 9.60 RM
Return Walls 4 1 x 6 x 1.10 = 6.60 RM
1 x 6 x 1.60 = 9.60 RM
Pipe Culvert 2 x 6 x 1.10 = 13.20 RM
2 x 6 x 1.60 = 19.20 RM
2 x 6 x 2.10 = 25.20 RM
Total Qty. 489.60 RM
--- PAGE 5 ---
S.N. Particulars Nos. Length Breadth Height Qty. Units