## PDF Content
Converted PDF Content
Original file: RETWALL BILL.pdf
S.No. Particulars. Quantity Rate Unit Amount
11 Earthwork in excavation for foundation of B-1
structure complete with all lift, dewatering, 1.1.4
shoring and shuttering etc. including
refilling of trenches in 250 mm layer, ramming,
watering and disposal of surplus soll within a
lead of 1000 meters, as per drawing and
technical Earth In excavation for foundation of
specification. [MORTH Specification: Clause
304]. in ordinary soll [MORTH Specification
clause 301] BY MECHANICAL MEANS Depth
upto 3m 935.74 Cum 57 P Cum 53337.32
2Earthwork In excavation for foundation of B-1
structure complete with all lift, dewatering, 1.3.2
shoring and shuttering etc. including
refilling of trenches in 250 mm layer, ramming,
watering and disposal of surplus soil within a
lead of 1000 meters, as per drawing and
technical Earth in excavation for foundation of
specification. [MORTH Specification Clause
304].In Ordinary/Soft rock (not requiring
blasting) [MORTH Specification: Clause 3011
BY MECHANICAL MEANS 382.44 Cum 83 P Cum 31742.51
3Structural cement concrete (Design Mix) in
open foundations, with form work, at level.
Cement concrete for plain/reinforced concrete
in open foundations as per drawing and
technical specification. [MORTH Specification:
Section 1700 & 1500).
With 20mm nominal size aggregate
P.C.C. M-15 grade 93.57 Cum 3038 P Cum 284278.57
4Structural cement concrete for plain concrete/
reinforced concrete for substructure at any
level, complete as per [MORTH Specification:
Section 1500 & 1700]. drawing and technical
specification. Design mix concrete PCC M-15
Upto 5 mtr. Height 1863.99 cum 3666 P Cum 6833377.26
6Providing A.C. pipe Weep holes 150mm B-3
dia in Masonry/plain Concrete/Reinforced 13
Concrete abutment, wing wall/return wall
complete as per drawing and technical
specification. [MORTH Specification : Clause
2205]. 489.60 R mtr 114 P RM 55814.40
Total Rs. 7258550.06RETAINING WALLS (PADLI GUJARESHWAR)
ABSTRACT OF COST
S.N. Particulars Nos. Length Breadth Height Qty. Units
1Earthwork in excavation for foundation of
structure complete with all lift, dewatering,
1.1.4 shoring and shuttering etc. including
refilling of trenches in 250 mm layer,
ramming, watering and disposal of surplus
soll within a lead of 1000 meters, as per
drawing and technical Earth In excavation
for foundation of specification. [MORTH
Specification: Clause 304]. in ordinary soll
[MORTH Specification clause 301] BY
MECHANICAL MEANS Depth upto 3m
Return Walls 1 1 x 15 x 2.22 x 1.50 = 49.88 Cum
1 x 15 x 2.77 x 1.50 = 62.25 Cum
1 x 15 x 2.73 x 1.50 = 61.50 Cum
1 x 15 x 2.63 x 1.50 = 59.25 Cum
1 x 15 x 2.68 x 1.50 = 60.38 Cum
1 x 15 x 2.67 x 1.50 = 60.00 Cum
1 x 15 x 2.60 x 1.50 = 58.50 Cum
1 x 15 x 2.52 x 1.50 = 56.63 Cum
1 x 15 x 2.65 x 1.50 = 59.63 Cum
1 x 15 x 2.68 x 1.50 = 60.38 Cum
1 x 2 x 2.68 x 1.50 = 8.05 Cum
Return Walls 2 1 x 15 x 2.42 x 1.50 = 54.38 Cum
1 x 15 x 2.33 x 1.50 = 52.50 Cum
1 x 7 x 2.12 x 1.50 = 22.23 Cum
1 x 15 x 2.28 x 1.50 = 51.38 Cum
1 x 15 x 2.27 x 1.50 = 51.00 Cum
Return Walls 3 1 x 6.95 x 2.27 x 1.50 = 23.63 Cum
Return Walls 4 1 x 6.9 x 2.68 x 1.50 = 27.77 Cum
Pipe Culvert 1 x 6.2 x 2.77 x 1.50 = 25.73 Cum
Pipe Culvert 1 x 7.4 x 2.77 x 1.50 = 30.71 Cum
Total Qty. 935.74 Cum
2Earthwork In excavation for foundation of B-
1 structure complete with all lift, dewatering,
1.3.2 shoring and shuttering etc. including
refilling of trenches in 250 mm layer,
ramming, watering and disposal of surplus
soil within a lead of 1000 meters, as per
drawing and technical Earth in excavation
for foundation of specification. [MORTH
Specification Clause 304].In Ordinary/Soft
rock (not requiring blasting) [MORTH
Specification: Clause 3011 BY
MECHANICAL MEANS
Return Walls 1 1 x 15 x 2.22 x 0.45 = 14.96 Cum
1 x 15 x 2.77 x 0.50 = 20.75 Cum
1 x 15 x 2.73 x 1.25 = 51.25 Cum
1 x 15 x 2.63 x 1.90 = 75.05 Cum
1 x 15 x 2.68 x 0.90 = 36.23 Cum
1 x 15 x 2.67 x 0.45 = 18.00 CumRETAINING WALLS (PADLI GUJARESHWAR)
DETAILS OF MEASUREMENTS
S.N. Particulars Nos. Length Breadth Height Qty. Units
1 x 15 x 2.60 x 0.60 = 23.40 Cum
1 x 15 x 2.52 x 0.75 = 28.31 Cum
1 x 15 x 2.65 x 0.25 = 9.94 Cum
1 x 15 x 2.68 x 0.35 = 14.09 Cum
1 x 2 x 2.68 x 0.35 = 1.88 Cum
Return Walls 2 1 x 15 x 2.42 x 0.30 = 10.88 Cum
1 x 15 x 2.33 x 0.35 = 12.25 Cum
1 x 7 x 2.12 x 0.35 = 5.19 Cum
1 x 15 x 2.28 x 0.35 = 11.99 Cum
1 x 15 x 2.27 x 0.35 = 11.90 Cum
Return Walls 3 1 x 6.95 x 2.27 x 0.45 = 7.09 Cum
Return Walls 4 1 x 6.9 x 2.68 x 0.50 = 9.26 Cum
Pipe Culvert 1 x 6.2 x 2.77 x 0.50 = 8.58 Cum
Pipe Culvert 1 x 7.4 x 2.77 x 0.56 = 11.47 Cum
Total Qty. 382.44 Cum
3Structural cement concrete (Design Mix) in
open foundations, with form work, at level.
Cement concrete for plain/reinforced
concrete in open foundations as per drawing
and technical specification. [MORTH
Specification:
Section 1700 & 1500).
With 20mm nominal size aggregate
P.C.C. M-15 grade
Return Walls 1 1 x 15 x 2.22 x 0.15 = 4.99 Cum
1 x 15 x 2.77 x 0.15 = 6.23 Cum
1 x 15 x 2.73 x 0.15 = 6.15 Cum
1 x 15 x 2.63 x 0.15 = 5.93 Cum
1 x 15 x 2.68 x 0.15 = 6.04 Cum
1 x 15 x 2.67 x 0.15 = 6.00 Cum
1 x 15 x 2.60 x 0.15 = 5.85 Cum
1 x 15 x 2.52 x 0.15 = 5.66 Cum
1 x 15 x 2.65 x 0.15 = 5.96 Cum
1 x 15 x 2.68 x 0.15 = 6.04 Cum
1 x 2 x 2.68 x 0.15 = 0.81 Cum
Return Walls 2 1 x 15 x 2.42 x 0.15 = 5.44 Cum
1 x 15 x 2.33 x 0.15 = 5.25 Cum
1 x 7 x 2.12 x 0.15 = 2.22 Cum
1 x 15 x 2.28 x 0.15 = 5.14 Cum
1 x 15 x 2.27 x 0.15 = 5.10 Cum
Return Walls 3 1 x 6.95 x 2.27 x 0.15 = 2.36 Cum
Return Walls 4 1 x 6.9 x 2.68 x 0.15 = 2.78 Cum
Pipe Culvert 1 x 6.2 x 2.77 x 0.15 = 2.57 Cum
Pipe Culvert 1 x 7.4 x 2.77 x 0.15 = 3.07 Cum
Total Qty. 93.57 Cum
S.N. Particulars Nos. Length Breadth Height Qty. Units
4Structural cement concrete for plain
concrete/ reinforced concrete for
substructure at any level, complete as per
[MORTH Specification: Section 1500 &
1700]. drawing and technical specification.
Design mix concrete PCC M-15 Upto 5 mtr.
Height
Return Walls 1 1 x 15 x 1.92 x 2.9 = 83.38 Cum
1 x 15 x 2.47 x 4.1 = 151.70 Cum
1 x 15 x 2.43 x 4.3 = 156.95 Cum
1 x 15 x 2.33 x 4.3 = 150.50 Cum
1 x 15 x 2.38 x 4.3 = 153.73 Cum
1 x 15 x 2.37 x 4.25 = 150.88 Cum
1 x 15 x 2.30 x 4.35 = 150.08 Cum
1 x 15 x 2.22 x 4.1 = 136.33 Cum
1 x 15 x 2.35 x 4.2 = 148.05 Cum
1 x 15 x 2.38 x 4.3 = 153.73 Cum
1 x 2 x 2.38 x 4.3 = 20.50 Cum
Return Walls 2 1 x 15 x 2.12 x 2.90 = 92.08 Cum
1 x 15 x 2.03 x 2.95 = 89.98 Cum
1 x 7 x 1.82 x 2.60 = 33.06 Cum
1 x 15 x 1.98 x 2.95 = 87.76 Cum
1 x 15 x 1.97 x 2.90 = 85.55 Cum
Return Walls 3 1 x 6.95 x 4.6 x 0.15 = 4.80 Cum
Return Walls 4 1 x 6.9 x 4.85 x 0.15 = 5.02 Cum
Pipe Culvert 1 x 6.2 x 4.85 x 0.15 = 4.51 Cum
Pipe Culvert 1 x 7.4 x 4.9 x 0.15 = 5.44 Cum
Total Qty. 1863.99 Cum
5Providing A.C. pipe Weep holes 150mm B-
3 dia in Masonry/plain Concrete/Reinforced
13 Concrete abutment, wing wall/return wall
complete as per drawing and technical
specification. [MORTH Specification :
Clause 2205].
Return Walls 1 1 x 102 x 1.10 = 112.20 RM
1 x 102 x 1.60 = 163.20 RM
Return Walls 2 1 x 46 x 1.10 = 50.60 RM
1 x 46 x 1.60 = 73.60 RM
Return Walls 3 1 x 6 x 1.10 = 6.60 RM
1 x 6 x 1.60 = 9.60 RM
Return Walls 4 1 x 6 x 1.10 = 6.60 RM
1 x 6 x 1.60 = 9.60 RM
Pipe Culvert 2 x 6 x 1.10 = 13.20 RM
2 x 6 x 1.60 = 19.20 RM
2 x 6 x 2.10 = 25.20 RM
Total Qty. 489.60 RM
S.N. Particulars Nos. Length Breadth Height Qty. Units